## Register
NHS Rotherham Clinical Commissioning Group – Risk Register
Ref | Entry date | Lead Officer | Risk Description | Risk Cause | Risk Consequence | Financial Risk | Risk rating |  |  | Assurance / Control | Actions | Date reviewed | Links to Governing Body Assurance Framework /Issues Log
[7 empty] | L | C | T
RR0 | 18.11.20 | Chief Officer | Coronavirus (COVID19) Pandemic - CCG can't deliver Strategic Plan or key waiting targets | Coronavirus (COVID 19) Pandemic | CCG can't deliver Strategic Plan or key waiting targets |  | 5 | 4 | 20 | New planning guidance released with targets for recovery in Elective Care and Cancer | Planning Team established and overseen by Place Delivery Team. Revised recovery plan being written | CE 18.11.20 OE 18.12.20 IA 07.04.21 OE 09.04.21 CE 10.05.21 | ALL
RR3 | 29.11.2016 | Chief Officer | Not maintaining accessible and high quality primary care as a consequence of recruitment issues | High numbers of GPs and practice nurses in Rotherham aged 55-59 and insufficient new trainees coming in to replace and insufficient providers using new workforce models | Inability for providers to continue delivering all requirements and ultimately may have to cease all provision causing more pressure on other providers. | Increase in non elective hospital admissions and non delivery of CCG QIPP activity at hospital up to £20m | 2 | 4 | 8 | Primary care strategy has been agreed and implementation has begun. LTP is providing the opportunity to support practice resilience at pace however practice engagement with new workforce models continues to impact. The formation of PCN s will further increase resilience Additional Roles Scheme for Primary Care. Additional pharmacists and other additional roles. | to work with PCNs to recruit to additional roles | OE 24.04.17 OE 22.12.17 OE 16.02.18 OE 16.03.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 OE 21.02.19 OE 15.02.19 OE 22 03 19 IA 05.06.19 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 CE18.11.20 OE 18.12.20 OE 09.04.21 CE 10.05.21 | GBAF2
RR10 | 05.01.2017 | Chief Finance Officer | Financial pressures in social care may result in reduction in investments upon which healthcare services are reliant | Lack of capacity in wider services leading to reduced support for specific patient groups. | CCG’s objectives to reduce admissions and safely support patients in alternative setting may be compromised. | Additional in year risk currently assessed as minimal to £0m | 3 | 4 | 12 | The Rotherham place plan commits all partners to the delivery of joint objectives and organisations will be held to account by each other The Rotherham Accountable Care Partnership governance and Improved Better Care Fund governance arrangements support containing the level of risk. |  | WA 22.09.17 OE 13.10.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 OE 21.02.19 OE 15.02.19 OE 22 03 19 WA 05.06.19 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 WA 27.10.20 OE 18.12.20 WA 16.02.21 OE 09.04.21 WA 10.05.21 | GBAF3
RR11 | 05.01.2017 | Chief Finance Officer | Insufficient funds to finance CCG planned objectives on a recurrent basis | Levels of allocation growth being insufficient to fund demand and price inflationary pressures, and fund local and national investment priorities. | A sustained efficiency requirement. | The CCG had a residual forecast gap of circa £5.6m based on its initial M7-12 2020-21 planning sibmission. The CCG would expected to have a circa £12m recurrent gap in 2021-22, (subject to confirmation of allocations and the national financial regime to be in operation) | 3 | 4 | 12 | 27-10-20 begin to identify / construct viable efficiency schemes. Identify other mitigating actions. Report progress monthly to Governing Body. Jan 2021 - update to GB on 2021-22 financial plan position and ,in the absence of planning guiance, range of scenarios based on modelled assumptions | Regular updates to GB . Intention to construct 2021-22 financial plan as planning guidance is received - currently expenct mid March 2021 | OE 24.04.17 OE 13.10.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 OE 21.02.19 OE 15.02.19 OE 22 03 19 WA 05.06.19 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 WA 27.10.20 OE 18.12.20 WA 16.02.21 OE 09.04.21 WA 10.05.21 | GBAF3
RR15 | 24.01.2017 | Executive Place Director | Failure to implement Special Educational Needs and Disability (SEND) reforms (part 3) of the Children and Families Act 2014/SEND Code of Practice. | Complexity of the new SEND reforms. Lack of assurance for the CCG due to non-attendance at the Education Health & Care Panel. CCGs failure to identify correct attendee at EHC panel | EHC plans agreed at panel become statutory documents and the CCG must provide health provisions stated in the plan. If the CCG does not have oversight of these plans it may result in the CCG having to provide non universal services. | £380k 19/20 | 3 | 4 | 12 | CCG completed a diagnostics self-assessment (provided by the council for disabled children). A second assessment took place in January 2017. This covers all aspects of the SEND reforms. Further self-assessment has been completed in September 2017. SEND Sufficiency Plan now drafted, SEND Self-assessment now updated. SEND sufficiency plan now complete, £380k investment identified in CCG 19/20 plan. Awaiting further formal notfification of risks. | SEND sufficiency plan. SEND strategy and SHMI strategy received in OE and SCE March 2021 | OE 24.04.17 OE 13.10.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 IA 21.02.19 OE 15.02.19 OE 22 03 19 IA 05.06.19 02.08.19 OE 04.10.19 OE 10.03.20 IA 16.12.20 Oe 18.12.20 IA 22.2.21 IA 07.04.21 OE 09.04.21 IA 10.05.21 | GBAF4
RR16 | 31.01.2017 | Chief Officer | Risk of some hospital services not being sustainable. Eg Stroke / Gastro / Maternity / Paeds / Urgent Care Services are currently commissioned on South Yorkshire & Bassetlaw footprint and sustainability of hospital services is being reviewed. | Some services may no longer be provided by our local acute providers. | Risk around sustainability of local services may mean Rotherham patients to travel to other areas | Potential risk of £1 - 2m for reconfiguration of hyper acute stroke. Potential finance risk will be identified through the model | 4 | 4 | 16 | SY+B Accountable Care System commissioned a review by April 2018 to asses hospital sustainability. 5 priority areas have been selected and oversight will be through the CCG GB. SY&B 2018 review work streams - Peads/Maternity/Gastro/Urgent Care. SY ICS are sustaining loal services SYB commissioning five priorty areas across ICS to maintain sustainability. Looking at standards across hospitals. | Supporting projects where appropriate to ensure patients are not disdvantaged and that the hospital remains sustainable | OE 24.04.17 OE 13.10.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 OE 21.02.19 OE 15.02.19 OE 22 03 19 CE 05.06.19 OE 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 CE 18.11.20 OE 18.12.20 OE 09.04.21 CE 10.05.21 | GBAF1
RR19 | 06.02.2017 | Executive Place Director | Sustainability of improvement in the quality of service in relation to CAMHS in Rotherham, increasing presentation for Eating Disorders. | Under transformation of services linked into the delivery of the Local Transformation Plan, increase in prevalence of Eating disorders linked to Covid 19 pandemic | Unmet need leading to increased acuity in presentation. Continued dissatisfaction in the service by GPs, families and young children | None | 3 | 4 | 12 | Weekly meeting between RCCG, RDASH, CAMHS & TRFT. Monthly CAMHS contract performance meeting. | Align sub-regional response to RDASH business case, additional investment into community eating disorders service approved by OE. | OE 24.04.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 IA 21.02.19 OE 15.02.19 OE 22 03 19 IA 05.06.19 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 IA 16.12.20 OE 18.12.20 IA 22.2.21 IA 07.04.21 OE 09.04.21 JL 03.05.21 IA 20.05.21 | GBAF3
RR30 | 11.04.2018 | Chief Finance Officer | Financial risk due to medication either not being available, necessitation the substitution on a more expensive alternative, or not available at the agreed drug tariff price. The risk is that levels of such inflation in any one year, significantly exceed the levels seen in any previous year. | Pharmaceuticals are commodities freely traded in international markets. Issues including exchange rate fluctuation , supply and demand impact. The consolidation of manufacturers and suppliers results in reduced competition and an increasing number of product shortages. The established price of products cannot be guaranteed when supply is compromised. | Volatility of the price of pharmaceuticals can place sudden cost pressures the CCGs prescribing budget. | £0 at start of year . To be assessed in year based on actual performance. | 2 | 4 | 8 | The prescribing budget provides for some degree of price inflation. Actual performance is continually monitored and mitigating actions where possible are put in place by the CCG Med Management Team. | Monthly monitoring of actual prescribing spend vs budget by MMT and Finance Teams. Horizon scanning by MMT. Receipts of Regional drugs data comparisons and horizon scanning. Medications supply issues alerts from central and regional NHS sources.MMT workclosely in conjunction with GP practices in Rotherham and are well placed to pick up on issues manifesting locally. | SL 11.04.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 OE 21.02.19 OE 15.02.19 OE 22 03 19 WA 05.06.19 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 WA 27.10.20 OE 18.12.20 WA 16.02.21 OE 09.04.21 WA 10.05.21 | GBAF3
RR46 | 09.09.19 | Chief Finance Officer | The CCG is required to manage fraud risk in line with its overall risk management policy. A range of risks exist relating to potential fraud, and are identified as part of the counter fraud risk assessment process. This risk assessment has identified 28 Primary Fraud Risk areas, and is documented separately . Rather than duplicate the 28 areas within this register , this entry in the risk register is to acknowledge a seperate risk assessment exists. | Fraudulent activity | Could include potential financial losses and potential reputational damage. | not quantifiable on a blanket basis | RR46 - Fraud Standard 1 4 - Appendix A Link.pdf |  |  | A separate Counter Fraud Risk Assessment exercise is carried out by the CCG's Counter Fraud service. 28 Primary Fraud Risk areas were identiied in the 2019-20 counter fraud plan. A range of assurance measures are put in place as a result of the risk assessments. | A range of assurance measures are put in place as a result of the risk assessments. | WA 13.09.19 OE 10.03.20 OE 16.04.20 OE 18.12.20 WA 16.02.21 OE 09.04.21 WA 10.05.21 | ALL
RR48 | 26.05.20 | Chief Officer | People facing the greatest deprivation are experiencing a higher risk of exposure to Covid-19 and existing poor health puts them at risk of more severe outcomes if they contract the virus. BME were at higher risk of contracting the virus and have poorer health outcomes. | Covid-19 | Institute for Fiscal Studies suggests BME patients dying disproportionately. Beyond the immediate harm caused by COVID-19 itself and the accompanying lockdown, there will be longer term implications on inequalities. | Not known | 3 | 3 | 9 | Restoration plans BAME risk assessment for CCG Staff All providers completed risk assessment | At risk groups will be prioiritsed as part of mass vaccination programme | Added - 26.05.20 CE 18.11.20 OE 18.12.20 OE 09.04.21 CE 10.05.21 | GBAF2 GBAF3
RR51 | 2020-11-06 | Chief Finance Officer | Funding assumptions underpinning the M7-12 balanced plan do not materialise as per the plan. | Subsequent changes to national guidance ( eg on HDP Schemes) Subsequent changes to ICS stance ( eg on share of System Growth allocation). Subsequent changes to regional guidance ( eg on ARRS and SDP, and potentially drawdown ). | Adverse/ favourable impact on in-year performance | Most likely range £1.3 - £4m adverse | 1 | 1 | 2 | Monthly monitoring of financial position. Monthly reporting of risks and mitigations | Reporting of risks to financial position in monthly GB finance report. Monthly reporting of risks and mitigations to GB via separate report.Minimal residual risk to financial position reported at M11, | added 09.11.20 OE 18.12.20 WA 16.02.21 WA 09.04.21 WA 10.05.21 | ALL
RR52 | 2020-11-06 | Chief Finance Officer | forecast outturn assumptions underpinning the M7-12 balanced plan do not materialise as per the plan. | Expenditure actuals do not conform to the levels forecast at the time of planning. This could be due to price changes, volume changes, case mix changes in any area of the CCGs portfolio. This could also be caused by an external pressure outside of the direct CCG control ( ie financial pressure from the wider ICS) | Adverse/ favourable impact on in-year performance | Most likely range -£2m to £2m | 1 | 1 | 2 | Monthly monitoring of financial position. Monthly reporting of risks and mitigations | Reporting of risks to financial position in monthly GB finance report. Monthly reporting of risks and mitigations to GB via separate report . Minimal residual risk to focast outturn reported at M11 | added 09.11.20 OE 18.12.20 WA 16.02.21 WA 09.04.21 WA 10.05.21 | ALL
RR53 | 2020-10-27 | Chief Finance Officer | Financial pressures in wider Place partners result in reduction in investments upon which CCG commissioned services are either co-dependant or reliant. | Financial pressures on all partners to balance budgets | Additional financial pressure being applied to or transferred to the CCG | Additional in year risk currently assessed as minimal to £0m | 3 | 3 | 9 | The Rotherham place plan commits all partners to the delivery of joint objectives and organisations will be held to account by each other The Rotherham Accountable Care Partnership governance and Improved Better Care Fund governance arrangements support containing the level of risk. |  | OE 18.12.20 WA 16.02.21 OE 09.04.21 WA 10.05.21 | GBAF3
RR54 (New) | 16.04.21 | Chief Officer | CCG transitioning into ICS. CCG must still deliver its duties during the transition year of 2021/22. | The publication of the "Integration and Innovation: working Together to Improve Health and Social Care for All" white paper which outlines the ambition for the ICS's to be established from 1st April 2022 and for the ICS's to take on the responsibilities of CCGs. Further guidance expected and development work ongoing at ICS and place level | Workforce received employment assurances (except GB members) |  | 3 | 3 | 9 | Governance Principles document. CCG represented on the SY&B ICS Workstreams. Commitment to Staff employment. HR principles developed nationally to support this transition and these will be available in April 2021. Well established Place Board. | Maintain appropriate governance arrangements and controls | CE 20.04.21 CE 10.05.21 | ALL
Risk Appetite 12
Risk Appetite 12
Risk Appetite 12
Risk Appetite 16
Risk Appetite 10
Risk Appetite 12
Risk Appetite 12
Risk Appetite 12
Risk Appetite 12
Risk Appetite 12
Risk Appetite 9
Risk Appetite 9
Risk Appetite 16
Risk Appetite 12
Risk Appetite 12
Risk Appetite 12
Risk Appetite 9

## Closed risks
Ref | Entry date | Lead Person | Risk Description | Risk Cause | Risk Consequence | Risk rating |  |  | Assurance & Actions | Date Last Change Made | Links to Governing Body Assurance Framework /Issues Log | Date Closed
[6 empty] | L | C | T
RR1 | 28.11.2016 | Alun Windle | CCG not hitting March 2017 deadline imposed by NHSE for the PUPoC claims process to complete | NHSE deadlines and extensive review process of NHS RCCG | Possible maladministration notice (unknown financial impact) for NHS RCCG | 1 | 5 | 5 | Action completed by end of January 2017. Closure requested. | OE 13.03.17 | N/A | OE 13.03.17
RR2 | 29.11.2016 | Jacqui Tuffnell | Insufficient funding transferred from NHS England for the provision of services (Obesity and CAMHS) | Collaborative commissioning of specialised services | Inability to procure required services and/or additional financial impact for RCCG | 1 | 4 | 4 | Awaiting national guidance. Discussions have taken place with NHSE to confirm that Rotherham patients are not disadvantaged | OE 13.03.17 JT 13.04.17 OE 21.04.17 | N/A | OE 21.04.17
RR4 | 29.11.2016 | Jacqui Tuffnell | Impact of PMS changes on the stability of practices | Changes in the funding arrangements for practices | Inability for providers to continue delivering all requirements and ultimately may have to cease all provision causing more pressure on other providers | 2 | 3 | 6 | PMS funding has been reinvested in practices. Other than youth clinics at Kiveton, no other services have ceased as a consequence of PMS changes | OE 13.03.17 JT 13.04.17 OE 21.04.17 | N/A | OE 21.04.17
RR6 | 13.12.2016 | Sue Cassin | Reputational risk to NHS RCCG and possible instability to Strategic Clinical Executive from CQC inspection of GP practices | CQC inspection of GP practice and resultant ratings | Need to support practices to take remedial action through the contract | 2 | 4 | 8 | PM forum, nurses forum, facilitation of information sharing, support via development of templates for collation of evidence. Support with areas of underachievement identified - | OE 13.03.17 OE 21.04.17 | GBAF 1 | OE 21.04.17
RR8 | 05.01.2017 | Keely Firth | TRFT operate within control total agreed with NHS Improvements for 2016/17 which is a deficit plan. If the trust cannot sustain the provision of services within its financial envelope the services may be withdrawn by the trust. | Lack of clinical capacity, rising costs for CNST and other non pay expenditure. Insufficient corporate capacity to focus on the changes required to deliver efficiencies. | Cost of buying capacity at premium rates. Cost of provision is greater than tariff income. | 4 | 4 | 16 | There is a national cap on locum and agency payments for FTs; FTs working together vanguard looking at vulnerable specialties; FT held to account by NHSI re quality and financial performance and HEE re clinical staffing | OE 13.03.17 OE 21.04.17 | N/A | OE 21.04.17
RR24 | 27.02.2017 | Rachel Garrison | Unable to process data and make payments to GP's and optometrists for work carried out | Significantly depleted staffing in the team. Currently carrying 30hour B4 vacancy, lost another B4 16 hours on 1st April, and will lose B5 16 hours at the end of May. Payments go through every month and can't be processed without support, 10 day window for payments to be processed, and will impact our ability to monitor the investment made in the Quality Contract and other schemes of work. Discussion at OE 27.02.17 | Cash flow into practices would be impacted, and for some this would cause serious problems | 3 | 3 | 9 |  | OE 24.04.17 OE 21.04.17 | GBAF 3 | OE 21.04.17
RR25 | 06.02.2017 | Kate Tufnell | NHS England unable to locate CAMHS Tier 4 Beds locally. | CAMHS Tier 4 beds are not ideally located geographically around the country. | As a result RDaSH may have to place under 18's with Rotherham's Adult beds - Risk Children in adult beds. Adult beds occupied (currently CCG not charging) could result in CCG having to fund out of area bed for Adult. (Emergency Issue) | 3 | 4 | 12 | The CCG commissions an Intensive Community Support service from RDaSH CAMHS which helps to avoid Tier 4 admissions. Part of this service includes a Paediatric Liaison Nurse who liaises with TRFT and NHS England concerning Tier 4 admissions. | NP 12.04.17 OE 21.04.17 | GBAF 1 | OE 21.04.17
RR27 | 12.04.2017 | Wendy Lawrence | The integrity and security of key information assets held on the CCG network could be at risk of cyber attacks. |  | Loss of critical business information. | 3 | 4 | 12 | The CCG routinely assesses cyber security risks via the IT SLA with TRFT. Provide updates from the IT SLA Meeting through to the IG Group specifically around cyber security and this is reported to Aqua | WA 12.04.17 OE 21.04.17 | N/A | OE 21.04.17
RR23 | 11.11.2011 | Sue Cassin | Quality of Commissioned Services | Inability of providers to deliver quality safe services. | Sub optimal care for patients resulting in poor outcomes. Loss of reputation for both provider and commissioner | 4 | 3 | 12 | Three officers are responsible for quality of each major contract area. For TRFT as largest contract we maintain quality assurance by monitoring the national quality standards within the NHS standard contract along with national and locally agreed Local Incentive Schemes. Participating in providers assurance meetings. Ad hoc and planned visits to provider units, including a programme of clinically led visits. Managing the assurance of responses to Serious Incidents on behalf of the NHSE. A wide range of benchmarking data is monitored including data on HSMRs and condition specific HSMRs peer, CQC risk ratings. Similar processes are in place for RDASH. A wide range of hard and soft intelligence is used through contract for assurance of GP quality. | OE 24.04.17 OE 16.06.17 | GBAF 1 | OE 16.06.17
RR7 | 05.01.2017 | Keely Firth | Failure to deliver QIPP programme for 2017/18 | Added costs in prescribing, planned care, unscheduled care | Higher levels of expenditure | 3 | 4 | 12 | Focus on waste by MM team; Protocols agreed for clinical thresholds; Plan B threshold list also developed by CCG clinicians. Block contract for non electives; Financial contingency in place. | OE 24.04.17 OE 16.06.17 | GBAF 1 | OE 16.06.17
RR21 | 13.2.2017 | Deputy Chief Officer | Failure to IAPT 6ww Access Target get (constitutional requirement) | Staffing challenges within TRFT impacting on the number of available diagnostic clinics | Low performance against the 6ww standard for which the CCG are held to account by NHSE, could impact on other Waiting Time targets if not resolved. | 3 | 3 | 9 | CCG Chair RDASH contractual meetings, IAPT National Intensive Support team visited Rotherham and actions being taken to improve position, e.g. further training of Workforce, Self Referral. Agreed recovery trajectory in place to improve performance. | OE 24.04.17 OE 22.09.17 | N/A | OE 22.09.17
RR31 | 20.09.2017 | Chief Nurse | Suboptimal outcomes due to Minimal case and care management of S117 patients | Minimal service provision to S117 patients due to short to medium sickness of case manager. | No robust contingency within the CCG regarding skills and knowledge to provide full service cover. | 3 | 3 | 9 | Interim minimum cover from Head of CHC service for urgent CTR referrals and high level reporting to NHS England. S117 service is planned to merge with the CHC service once new web based Broadcare system fully implemented and administration cover for S117 service will be covered by CHC service in future. | AW 20.09.17 OE 17.11.17 | N/A | OE 17.11.17
RR22 | 13.2.2017 | Deputy Chief Officer | Delivery of Child and Adolescent Mental Health Services (CAMHS) Transformation, Waiting Times and lack of improvement in the quality of service | Mobilisation of the new CAMHS Model, increase referrals impacting on the ability to deliver access times | Transformation Plan is being delivered with significant recruitment into the CAMHS service. Waiting times for access remain challenging. Continued dissatisfaction in the service by GP's families and young children | 3 | 4 | 12 | CCG Chair CAMHS Strategy and Partnership Group and fortnightly CAMHS performance meeting. Recently agreed to develop a Section 75 agreement with RMBC for CAMHS. | OE 24.04.17 OE 22.12.17 OE 16.02.18 OE 16.03.18 OE 19.03.18 | N/A | OE 19.03.18
RR30 | 11.08.2017 | Chief Finance Officer | Greater than 'normal' adverse pressure on drugs budget | NHSE unplanned drug price reductions in 2017-18 not being made available to CCG to offset unplanned drug price increases (inlcuding costs of No Cheaper Stock Obtainable (NCSO's) which the CCG experiences. | Additional cost pressure have been successfully managed within the prescribing budget. | 1 | 3 | 3 | Reporting of risks through GB finance report. | WA 11.08.17 OE 22.12.17 OE 16.02.18 OE 16.03.18 OE 19.03.18 | GBAF 2 | OE 19.03.18
RR18 | 02.02.2017 | Deputy Chief Officer | Increased demand in the 111 service and patients accessing other services inappropriately | Number of referrals and patient contacts. Capacity of the service. | Patients currently in inappropriate destinations e.g. A&E. Impact on demand management. | 3 | 4 | 12 | Capacity versus Demand is monitored through the contract. Although usage has increased this is not above the contracted capacity at present | OE 24.04.17 OE 22.12.17 OE 16.02.18 OE 16.03.18 OE 01.06.18 OE 13.06.18 | GBAF1 | OE 13.06.18
RR19 | 06.02.2017 | Deputy Chief Officer | Sustainability of improvement in the quality of service in relation to CAMHS in Rotherham | Under transformation of services linked into the delivery of the Local Transformation Plan | Continued dissatisfaction in the service by GPs, families and young children | 3 | 4 | 12 | Fortnightly CAMHS Update meeting, Monthly CAMHS contract performance meeting. Local Transformation Plan monitored through LTP Action Plan. Positive Q4 Assurance received | OE 24.04.17 OE 22.12.17 OE 16.02.18 OE 16.03.18 OE 01.06.18 OE 13.06.18 | GBAF1 | OE 13.06.18
RR29 | 11.08.2017 | Chief Finance Officer | NHS England System Risk Reserve 2017-18 fails to deliver to the level NHSE require nationally will need deleting at the end of March | Lack of financial balance across the health sector | NHSE may come back to CCG's in-year during 2017-18 for contributions beyond that expected by the business rules currently . | 2 | 3 | 6 | Reporting of risks through GB finance report. | WA 11.08.17 OE 22.12.17 OE 16.02.18 OE 16.03.18 OE 01.06.18 OE 13.06.18 | GBAF2 | OE 13.06.18
RR7 | 05.01.2017 | Chief Finance Officer | Failure to deliver QIPP programme for 2018/19 | Added costs in prescribing, planned care, unscheduled care | Higher levels of expenditure | 3 | 4 | 12 | Focus on waste by MM team; Protocols agreed for clinical thresholds; Plan B threshold list also developed by CCG clinicians. Block contract for non electives; Financial contingency in place. | OE 24.04.17 OE 13.07.18 OE 24.08.18 OE 12.10.18 | GBAF2 | WA 16.10.18
RR18 | 02.02.2017 | Deputy Chief Officer | Increased demand in the 111 service and patients accessing other services inappropriately | Number of referrals and patient contacts. Capacity of the service. | Patients currently in inappropriate destinations e.g. A&E. Impact on demand management. | 3 | 4 | 12 | Capacity versus demand is monitored through the contract. Although usage has increased this is not above the contracted capacity at present | OE 24.04.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 | GBAF1 | OE 16.11.18
RR20 | 13.2.2017 | Deputy Chief Officer | Failure to deliver "six week wait" diagnostic standards (constitutional requirement) | Underperformance in Echocardiography at Sheffield Teaching Hospital | Low performance against the 6ww standard for which the CCG are held to account by NHSE, could impact on other Waiting Time targets if not resolved. | 4 | 3 | 12 | System wide working across SY&B ICS to develop an improved position. Expectation that improvement will be seen in Q1 18/19. | OE 24.04.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 IA 20.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 | GBAF1 | IA 20.11.18
RR32 | 30.05.18 | Head of Commissioning | The impact of delivery of services (particularly extended access) in primary care and the new locality arrangements without a fully functioning federation | Delays in the Federation obtaining CQC registration impacting the ability to hold an APMS contract. Delay in agreeing the arrangements for localities. | Non-delivery of extended access by the national requirement of October 2018. Non-delivery of primary care networks (localities) by March 2019 | 4 | 3 | 12 | Regular meetings with the Federation and Extended Access hub leads to review progress. Identified cut-off dates for progress to revert to a secondary plan for delivery | JT 05.06.18. OE 13.07.18 OE 24.08.18 OE 12.10.18 | GBAF2 | JT 20.11.18
RR28 | 24.05.2017 | Chief Finance Officer | Failure to deliver Quality Innovation Productivity and Prevention (QIPP) programme for 2018-19 | Activity and/or price varying significantly in-year from QIPP modelling assumptions used at planning stage. Failure to gain operational traction on schemes in line with modelling assumptions; Either or both scenarios would present some degree of risk to financial balance. | Need to find alternative mechanisms to delivering financial plan. | 2 | 4 | 8 | Quality Impact assessments have been undertaken and signed off by clinicians; Significant risk mitigated by a combination of actions including a block contract and nationally prescribed contingencies. Statements of QIPP performance covering both financial and operational performance presented at Governing Body. Financial risks and mitigations statement presented at Governing Body during the year. | WA 22.09.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 OE 21.02.19 OE 15.02.19 OE 22 03 19 | GBAF2 | MJ 22 03 19
RR7 Remove and replace with dates | 05.01.2017 | Chief Finance Officer | Failure to deliver QIPP programme for 2018/19 | Added costs in prescribing, planned care, unscheduled care | Higher levels of expenditure | 3 | 4 | 12 | Focus on waste by MM team; Protocols agreed for clinical thresholds; Plan B threshold list also developed by CCG clinicians. Block contract for non electives; Financial contingency in place. New schemes for QIPP plan - WA | OE 24.04.17 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 21.02.19 OE 15.02.19 OE 22 03 19 | GBAF2 | MJ 22 03 19
RR29 | 11.08.2017 | Chief Finance Officer | NHS England System Risk Reserve 2017-18 fails to deliver to the level NHSE require nationally will need deleting at the end of March | Lack of financial balance across the health sector | NHSE may come back to CCG's in-year during 2017-18 for contributions beyond that expected by the business rules currently . | 2 | 3 | 6 | Reporting of risks through GB finance report. | WA 11.08.17 OE 22.12.17 OE 16 2 18 OE 16.03.18 OE 01.06.18 WA 04.01.19 WA 21.02.19 OE 15.02.19 OE 22 03 19 | GBAF2
RR9 retire and replace with PC Newworks - IA | 05.01.2017 | Deputy Chief Officer | Failure delivering locality working as per Rotherham Place Plan | Refocusing of TRFT corporate capacity; Clinical governance risk across multi-professional groups; Interoperability of clinical systems. | Objectives not achieved to integrate care in localities and other risks under more pressure eg A&E and non elective admissions. | 3 | 4 | 12 | The Rotherham place plan commits all partners to the delivery of joint objectives and organisations will be held to account by each other. The evaluation of the Locality Pilot will report in January 2018. External support to Rotherham Place to support delivery of locality work. Discussion now moving forward regarding establishmnet Primary Care Networks this may supercede loclaity working. | OE 24.04.17 OE 13.10.17 OE 22.12.17 OE 16.02.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 IA 21.02.19 OE 15.02.19 OE 22 03 19 | GBAF2 | IA 22 03 19
RR27 Retire and replace | 24.05.2017 | Chief Finance Officer | TRFT are operating to a deficit plan and do not have an agreed control total with NHS Improvement for 18-19. | Multiple factors , culminating in costs or service provision exceeding income recovered. | If the Trust cannot provide services sustainably, individual services may require to be remodelled or reconfigured or the overall portfolio of services being offered may require to be changed. . | 4 | 4 | 16 | There is a national cap on locum and agency payments for Foundation Trusts (FT); Acute FTs working together vanguard looking at vulnerable specialties; FT held to account by NHS Improvement re quality and financial performance and Health Education England (HEE) re clinical staffing. NHSE/NHSI/ICS 'system meetings' regarding TRFT Control Total and financial position, CCG Chief Finance Officer (CFO) and Deputy Chief Officer (DCO) in regular joint dialogue with TRFT DoF and COO, creation of shared 5 year plan . | WA 22.09.17 OE 22.12.17 OE 16 2 18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 OE 21.02.19 OE 22 03 19 | GBAF2 | MJ 22 03 19
RR26 | 15.03.2017 | Assistant Chief Officer Suggest retirement - BCM cascade test activated in anger two weeks ago - BCM plan worked. Work will continue just not required on the risk register going forward. | Business Continuity Planning | Business Continuity Planning is not embedded within the CCG which could lead to a lack of organisational resilience | The Business Continuity Management Plan may not work and business may be disrupted. | 3 | 3 | 9 | Business Continuity Policy & Plan is in place. Meetings being arranged with teams to develop BCM in teams. BCM Presentation at Staff Briefing. BCM Exercise planned for January 2019 all staff meeting to test plans.BCM exercise carried out in Jan 2019 - meeting with staff teams to embed learning. | OE 24.04.17 RN 11.07.17 RN 28.09.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 RN 21.02.19 OE 15.02.19 OE 22 03 19 | GBAF 5 | RN 05 06 19
RR29 REMOVE COMPLETELY OBSCOLETE | 11.08.2017 | Chief Finance Officer | NHS England System Risk Reserve 2017-18 fails to deliver to the level NHSE require nationally will need deleting at the end of March | Lack of financial balance across the health sector | NHSE may come back to CCG's in-year during 2017-18 for contributions beyond that expected by the business rules currently . | 2 | 3 | 6 | Reporting of risks through GB finance report. | WA 11.08.17 OE 22.12.17 OE 16 2 18 OE 16.03.18 OE 01.06.18 WA 04.01.19 WA 21.02.19 OE 15.02.19 | GBAF2 | WA 05 06 19
RR33 | 13.07.2018 | Chief Finance Officer | Adverse financial impact on the CCGs financial position arising from NHSE's Transforming Care Partnerships initiative. | Changing data collection process and changing costing and calculation methodologies being utilised by NHSE to calculate the financial impact of patients transferring out of NHSE responsibility and into CCG commissioning responsibility. The generally high cost nature of the placements being required to put in place by CCGs to appropriately care for patients being transferred back from NHSE. | TCP Partnerships locally are unable to be clear what funding will transfer from NHSE Spec Comm into the TCP. CCG's within the TCP footprint are consequently unable to be clear what the precise financial impact to them in-year will be. | 4 | 3 | 12 | RCCG have made provision for the impact of currentl known patients in the 2019-20 financial plan. Doncaster CCG (as TCP host) continue to convey back to NHSE concerns regarding the process and the calculation methodology being used by NHSE, and are being proactive is suggesting what data and in what format NHSE should collect and calculate data. RCCG Officers (from within finance and clinical operational / contracting team continue to work closely with Doncaster CCG. Update as At March 2018 : (a). NHSE have recently advised their calculation metholodgy will , again, change. (b) RCCG have received an allocation £200k towards total costs in 2018-19 (c) given point (a), SYB CFO's have agreed this allocation adjustment will be non-recurrent until NHSE have settled on their final calculation methodology, Meanwhile the CCG is picking up full costs of patients through normal reporting and through 2019-20 financial plan. | WA 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 WA 04.01.19 WA 21.02.19 OE 15.02.19 OE 22 03 19 WA 28.03.19 | GBAF2 | WA 5 06 19
RR39 REMOVE OBSCOLETE | 24.05.2017 | Chief Finance Officer | TRFT are operating to a deficit plan and do not have an agreed control total with NHS Improvement for 2018-19.. | Multiple factors , culminating in costs or service provision exceeding income recovered. | If the Trust cannot provide services sustainably, individual services may require to be remodelled or reconfigured or the overall portfolio of services being offered may require to be changed. . | 4 | 4 | 16 | This risk can be removed from the Register w.e.f. April 2019 as TRFT will agree a control total with NHSI | OE 22 03 19 WA 28.03.19 | GBAF 2 | WA 05.06.19
RR31 | 13.05.2018 | Chief Nurse | Failure to maintain quality indicators in commissioned services which could result in harm to patients and organisational reputation. | Lack of ability to maintain quality indicators in commissioned services | Significant Harm/Death of patients reputation of service | 4 | 3 | 12 | Contract quality and performance monitoring in place - Quality Risk Profiling to asses current Risk and Appreciative Enquiry Process . Clinically led visits to providers. Established SI monitoring processes Clinically led visits to providers. Established SI monitoring processes. Monitoring of action plan in response to CQC recommendations. | AW 04.05.18 OE 01.06.18 OE13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 SC 21.01.19 OE 21.02.19 OE 15.02.19 OE 22 03 19 SC 05.06.19 | GBAF1 | SC 13.06.19
RR12 | 05.01.2017 | Chief Finance Officer | Increasing costs of individual patients of continuing care | Growth in new patients requiring CHC, increasingcomplexity, and increasing costs of provision | Overspends on CHC and / or Specialist MH and LD Placements | 3 | 4 | 12 | Robust application of the legal framework by the CHC team. Recognised and reported as a financial risk to Governing Body. Flagged to the ICS (via QIPP3 and 4 interactions with Deloittes) as being an area of potential concern. CCG commissioning external support to undertake review of service, commencing January 2019 , now concluded. At March 2019 OE considering report recommendations. 2019-20 financial plan updated to address increased levels of spend | OE 24.04.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 WA 04.01.19 WA 21.02.19 OE 15.02.19 OE 22 03 19 WA 28.03.19 WA 05.06.19 | GBAF3 | WA 04.06.19
RR41 (New) | 04.06.2019 | Chief Finance Officer | Financial risk relating to non-receipt of £6/head primary care investment monies | The CCG was advised to expect a separate primary care allocation for £6/head investment monies. This assumption is reflected in the plan | Non-receipt of the funding would require an immediate review of CCG planned investments in primary care. | 2 | 3 | 6 | CCG's were previously advised by NHSE to expect receipt of funds. RCCG's financial plan included this assumption, along with narrative to explain this- and this was accepted and not challenged by NHSE. Update at 04-07-19: Letter written to Richard Barker dated 21-06-19 received into the CCG confirming a non-recurrent £1.615m allocation will be transferred. | date 04-07-19: This risk can be removed from the Register. CHECK | GBAF 2 | WA 31.07.19
RR38 | 17.04.19 | Deputy Chief Officer | National requirement for all population to be included in Primary Care Networks | Risk to full population coverage if not all practices are included in the networks. Requirement to deliver extended access by network could impact the recently implemented arrangements | Exclusion of parts of the population and inability to access all services | 2 | 3 | 6 | Feedback from PLTC event Feedback from locality/networks as the become established MOU in place with the Federation to support practices with network development Communications to practices Organisation of PLTC to provide protected time for practices MOU with the Federation already in place to support development | OE 22 03 19 IA 05.06.19 02.08.19 OE 04.10.19 | GBAF 2 | JT 04.11.19
RR45 | 20.08.19 | Deputy Chief Officer | Inability to provide same day patient transport for TRFT discharges which will lead to delays to discharges | Contractual issues with the provider | Delays to hospital discharges resulting in A&E performance deterioration | 3 | 4 | 12 | Regular updates from the lead commissioner. All stakeholders aware of the concerns. RCCG has been involved in discussions with the lead commissioner (Barnsley) relating to the contractual issues. TRFT have been advised to plan as many discharges in advance as this service is provided by an alternative provider | JT 20.08.19 OE 04.10.19 | GBAF 2 | JT 17.12.19
RR34 | 07.12.18 | Deputy Chief Officer | The National Diabetes Prevention Programme Delivery. | NHS England have increased the capacity by 40% for initial assessments | Risk on delivery of target, which was already quite a stretch for Rotherham. Resource to get the scheme up and running in Rotherham, its going to need targeted referrals and publicity to really encourage self-referral and we're already stretched as a team. | 5 | 2 | 10 | RCCG Actions: - Requesting a sliding target so we build up to 40% increase. - The need for strong contract management moving forward. - Dedicated sites across the borough, offering day/evening and weekend sessions. - Linked to the APP - where eligible patients will get a push notification to say they are eligible for the scheme, with the promotional materials. RCCG Actions: - Requesting a sliding target so we build up to 40% increase. - The need for strong contract management moving forward. - Dedicated sites across the borough, offering day/evening and weekend sessions. - Linked to the APP - where eligible patients will get a push notification to say they are eligible for the scheme, with the promotional materials. - A new provider has been appointed and it is hoped that performance will improve | JM 07.12.18 IA 21.02.19 OE 15.02.19 OE 22 03 19 JT 17.04.19 IA 05.06.19 02.08.19 OE 04.10.19 | GBAF2 | JT 18.12.19 - Moved to Issues Log
RR44 | 12.06.19 | Deputy Chief Officer | TRFT Bed reconfiguration. Variation in number of hospital beds. | CQC concerns in relation to the staffing of the medicine bed base | Insufficient acute bed capacity impacting ED performance and patient care | 4 | 4 | 16 | Chief Nurse has been involved in teleconferences with CQC and the Trust. TRFT has redeployed staff from Breathing Space to support vacancies in the acute unit. TRFT has modelled bed requirements. Current contract is incentive based and provides protection against over performance . TRFT have undertaken a bed modelling exercise Discussions are continuing with TRFT in relation to the correct bed base and ability to safely staff | JT 11.6.19. 02.08.19 OE 04.10.19 | GBAF2 | JT 18.12.19 - Moved to issues Log
RR35 | 31.12.18 | Chief Officer | Reduced availability of pharmaceuticals and supplies imported from the EU | Risk on the availability of pharmaceuticals due to no deal EU Exit |  | 4 | 4 | 16 | MM Team identifying shortages and advising practices. Letter from Dept of Health and Social Care. Continue to work with Pharmacy colleagues in South Yorkshire and Bassetlaw and the wider Yorkshire and the Humber area. EU Operational Readiness Guidance DoHSC and NHS England and Improvement are developing arrangements to allow local and regional monitoring of stock levels . MM Team identifying shortages and advising practices. Likelihood increased from 3 to 4. | CE 31.12.18 OE 21.02.19 OE 15.02.19 OE 22 03 19 CE 05.06.19 02.08.19 OE 04.10.19 OE 10.01.20 | GBAF 2 | 10.01.20
RR36 | 23.04.19 | Chief Finance Officer | Disruption to CCG Business Intelligence, Information Governance and Data Protection Officer services | CCG failure to suitably reprovide or recommission services post expiry of the eMBED contract. | Issues in the delivery of performance reporting, information governance services and completion of the Data Security and Protection Toolkit. | 3 | 4 | 12 | Proposals are being developed and approved for the replacement of the eMBED Commissioning Support Services. The approach to replacing these services is being co-ordinated with SYB CCGs to determine where services could be shared. Model and JDs have been developed. Costed service models and associated job descriptions to be developed. Model and JDs have been developed. | AC 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 | GBAF 2 | 20.07.20
RR47 | 06.02.20 | Chief Officer | Coronavirus (COVID19) Pandemic | Coronavirus outbreak in Wuhan, China causing a global pandemic, resulting in serious illness and fatality. | The COVID-19 Pandemic has resulted in serious capacity issues across Rotherham in terms of health and social care capacity, suspension of statutory duties and financial impacts. | 5 | 5 | 25 | CCG CCG Incident Control Team set up and meeting regularly. Separate Issues Log set up updated twice weekly by Incident Control Team. Wider command and control system in place across Rotherham/ICS and NHSE. | OE 06.02.20 OE 10.03..20 OE 13.03.20 OE 16.04.20 | ALL | CE 16.11.20
RR18 | 02.02.2017 | Executive Place Director | Increased demand in the 111 service and patients accessing other services inappropriately | Number of referrals and patient contacts. Capacity of the service. | Patients currently in inappropriate destinations e.g. A&E. Impact on demand management. | 3 | 4 | 12 | Capacity versus Demand is monitored through the contract. Although usage has increased this is not above the contracted capacity at present | OE 24.04.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 IA 21.02.19 OE 15.02.19 OE 22 03 19 IA 05.06.19 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 IA 16.12.20 | GBAF1 | IA 16.12.20
RR50 | 2020-10-07 | Chief Finance Officer | CCG fails to set a balanced financial plan M7- 12 2020-21 | M7-12 known and expected financial allocations are below the level of forecast spend | Should RCCG declare a decit plan, it would trigger related governance and performance related consequences of doing so with NHSE and with other parties , noteablly external audit. | 4 | 5 | 20 | Live situation , being reported through CCG internal governance , and to NHSE/I through the ICS and CCG l financial planning returns and submissions , | CCG governing body continue to seek to be in a position to set a balanced financial plan , with the ICS recognising and formally acknowledging that to do so will directly and significantly increase delivery risk. 16/10/2020 - RCCG submitted a revised and balanced plan , in conjunction with SYB ICS, underpinned by forecasts revised to best-case scenarios, incorporating currently unidentified efficiency schemes, and with the ICS formally acknoweldging the lack of contingency to deal with significant forecast fluctuations and therefore with the associated and overall significantly increased financial and delivery risk. 04-11-20 GB Meeting formally accept M7-12 balance plan positions |  | WA 18.12.20
RR5 | 13.12.2016 | Chief Nurse | Reputational risk to NHS RCCG and individual risk to one or more Looked After Children | Low achievement of undertaking initial health assessments with statutory framework due to stringent monitoring of compliance a dip in data noted. In addition numbers of children coming into care is increasing at an unacceptable pace. | Not identifying health needs of children entering the care system and putting necessary care plans in place may result in harm. | 4 | 4 | 16 | Working closely with RMBC and TRFT to refresh processes and joint working to ensure children attend clinics. Peer review by Sheffield CCG. Reports received from Sheffield and RDaSH. RMBC Director of Childrens Services now leading the work stream with all partners. Looked after children numbers are closely monitored. LSCB 7.6.18 discussed the increase in LAC and the impact on agencies. This included TRFT and the IHAs and dental services. Further work being undertaken and will review at future LSCBs and Corporate Parenting. Further work being undertaken and will review at future LSCBs and Corporate Parenting. IHA target has been achieved for over 12 months, Named Dr for LAC in post. New nursing team will all be in post by end July 2020. Suggest removing this risk. | OE 24.04.17 OE 22.12.17 OE 16.02.18 OE 16.03.18 SC 11.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 SC 21.01.19 OE 15.02.19 OE 22 03 19 SC 05.06.19 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 SC 20.07.20 OE 18.12.20 SC 29.03.21 | GBAF4 | OE 09.04.21
RR14 | 09.01.2017 | Chief Officer | Failure to deliver A&E standards | Increased ambulance arrivals, and shortage of medical staffing and GP's/nurses at The Rotherham Foundation Trust (TRFT) . New model of UECC is still being developed | Low performance against the A&E standard for which the CCG are held to account by NHS England | 4 | 4 | 16 | CCG chair the A&E Delivery Board and there are detailed action plans to ensure that all enablers to the performance are optimised. Currently the trust is a national pilot for field testing national standards. Currently we are measuring against an average wait time and not 4 hour wait TRFT are a national pilot for new ways of measuring A&E performance using media waiting times. Improvement have been seen in Ambulance Handover tImes since Jan 2021 Winter Plan A&E Action Plan DTOC Action Plan Live reporting to CCG of A&E performance. | OE 24.04.17 OE 13.10.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 OE 21.02.19 OE 15.02.19 OE 22 03 19 JT 17.04.19 CE 05.06.19 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 CE 18.11.20 OE 18.12.20 IA 07.04.21 | GBAF1 | OE 09.04.21
RR17 | 31.01.2017 | Chief Nurse | Risk of lack of support to victims of Child Sexual Exploitation (CSE) due to the scale of criminal proceedings (and political issues as commissioners still have oversight Children’s services at the council- this has now been handed back to RMBC end 2018). Risk that funding will not be on-going. | Ongoing CSE criminal proceedings Both SYP and National Crime Agency. | Requiring additional mental health support for victims (both new and non recent). Reputational damage to CCG for Adult Mental Health/CAMHS . Funding to support NCA investigation requested from Health and Justice Commission. One year funding 2018/2019 with a further year available on positive evaluation. NHSE Health & Justice will attend in August to discuss funding for 20/21 | 2 | 4 | 8 | Children’s Board CCG Commissioning strategy CAMHS transformation plan Investment in Improving Access to Psychological Therapies services (Adult mental health) CCG Chief Nurse linked into national work by NHSE to develop 5 year strategy for Sexual Assault Services Additional funding for 2 years from NHS England has now been confirmed. Mental Health provision extended with additional funding from NHSE to encompass pre and during child support and exit strategy post trial. NHSE provided £100k for 2018/19 non recurrent to support counselling services for victims. Funding for further 3 years awarded by H&J, first and second evaluations of TRS very positive. (reduce risk rating - likelihood from 2 to 1) | OE 24.04.17 OE 22.12.17 OE 16.2.18 OE 16.03.18 OE 01.06.18 OE 13.07.18 OE 24.08.18 OE 12.10.18 OE 16.11.18 SC 21.01.19 OE 21.02.19 OE 15.02.19 OE 22 03 19 SC 05.06.19 02.08.19 OE 04.10.19 OE 10.03.20 OE 16.04.20 SC 20.07.20 OE 18.12.20 SC 29.03.21 | GBAF4 | OE 09.04.21
RR49 | 26.05.20 | Chief Officer | Vulnerability of voluntary sector partners post-Covid-19 | Covid 19 | Beyond the Covid pandemic, many of our Partner organisations from the voluntary sector will no longer exist (no longer financially viable). Going forward this will severely impact the delivery of services in the community - especially with regard to some of our most vulnerable communities - and have particular impact on being able to deliver Social Prescribing for Rotherham patients leading to further inequality. | 3 | 3 | 9 | CCG work closely with VAR to understand sustainability and support where we can. Support where appropairate is being provided by RMBC | Added - 26.05.20 CE 18.11.20 OE 18.12.20 | GBAF2 GBAF3 | OE 09.04.21
RR54 | 16.11.20 | Chief Officer | EU Exit - Access to prescription drugs | No deal EU Exit | Delays in access to prescription drugs due to EU Exit | 3 | 4 | 12 |  | CE 16.11.20 OE 18.12.20 | GBAF 1 GBAF 2 GBAF 3 | OE 09.04.21
RR55 | 18.12.20 | Chief Finance Officer | Dispensing/endorsing (non-party activity) | The Medicines Management team are observing a number of prescriptions where the community pharmacy claimed for the cost of a medicine being dispensed despite that medication being unavailable | Financial loss to CCG | 3 | 4 | 12 | EPACT data is provided monthly and reviewed and searched at least monhly by Meds Management Teams for accuracy and for anomolies. Anomolies including for suspected inappropriate claims for unavailable medicines are looked into. EPACT data searched by Meds Management Team at least monthly to identify possible false claims. Referals to Counter Fraud team made as and when they arise for appropriate opinion/investigation | OE 18.12.20 WA 16.02.21 | GBAF 2 | OE 09.04.21
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 15
Risk Appetite 15
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 12
Risk Appetite 12
Risk Appetite 12
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 16
Risk Appetite 12
Risk Appetite 12
Risk Appetite
Risk Appetite 10
Risk Appetite 12
Risk Appetite 10
Risk Appetite 12
Risk Appetite 12
Risk Appetite 9
Risk Appetite 12
Risk Appetite 12

## Scoring Matrix
Risk Matrix |  | Likelihood
|  | 1 | 2 | 3 | 4 | 5
|  | Rare | Unlikely | Possible | Likely | Almost certain
Consequence | 1 | 1 | 2 | 3 | 4 | 5
Negligible
| 2 | 2 | 4 | 6 | 8 | 10
Minor
| 3 | 3 | 6 | 9 | 12 | 15
Moderate
| 4 | 4 | 8 | 12 | 16 | 20
Major
| 5 | 5 | 10 | 15 | 20 | 25
Extreme
Risk Score | Risk Descriptor | Risk Appetite Statement
1-5 | Low | Averse Avoidance of risk and uncertainty is a key organization objective.
6-11 | Medium | Minimal Preference for ultra-safe options that are low risk and only have a potential for limited reward.
12-15 | High | Cautious Preference for safe options that have a low degree of risk and may only have limited potential for reward.
16-20 | Very High | Open Willing to consider all potential options and choose the one most likely to result in successful delivery, while also providing an acceptable level of reward and value for money.
25 | Extreme | Hungry Eager to be innovative and to choose options offering potentially higher business rewards, despite greater inherent risk.