## Sheet1
Meeting Date | Ref | Item | Action Required | Lead | Timescale | Status | Update
2017-03-01 | 239/16a | Patient Safety & Quality Assurance Report | Changes in legislation around Deprivation of Libertys guidance (lawful detainment of a patient who lacks capacity) need to be re-iterated to practices. These will be conveyed at PLTC and in the GP Bulletin. | Dr Kitlowski/ Mrs Cassin |  | Amber | message about last changes to go in GP news letter end March/beg April. Paper being drafted for OE outlining main changes expected following last review and Law Commission analysis of possible implications. (28/03/17). Awaiting guidance (3/5/17)
2017-04-01 | 08/17 | Delivery Dashboard | Deep dive into waiting times to be undertaken | Mr Atkinson |  |  | Complete reported in May
2017-06-01 | 07/17 | Delivery Dashboard | More information to be put in the narrative around TRFT A&E performance in future performance reports | Mr Atkinson |  |  | Complete reported in June
2017-06-01 | 07/17 | Delivery Dashboard | Mr Atkinson to include comparison data on the NHS111 service in the Performance Report once available | Mr Atkinson |  |  | Complete
2017-07-05 | 2017-08-01 | Performance Reports | Mr Barber requested the rag ratings to be reviewd | Mrs Allott | 2017-10-01 |  | Draft circulated as part of August GB information pack. Will be covered as part of QIPP report , on Sept GB Agenda
2017-07-05 | 2017-08-01 | Delivery Dash Board | Mr Atkinson agreed to provide a update on the urgent and Emergency Care Centre | Mr Atkinson | 2017-09-01 |  | Update will be covered in the performance section of the September meeting, report to be prepared following 3 monthsof activity
2017-07-05 | 2017-07-01 | Assurance Group | Ms Nutbrown and Ms Hague agreed to attend the Assurance Group meeting to discuss the Risk Regisiter | Mr Nutbrown & Mrs Hague | 2017-10-01 |  | Ms Nutbrown attended the Assurance group meeting on the 27 September 2017
2017-07-05 | 2017-05-01 | Chief Officers Report | Mr Edwards asked Mrs Henderson to confirm who from CCG should atttend the official opening of the Urgent and Emergency Care Centre in October | Mr Edwards | 2017-09-01 |  | the offical opening has now been confirmed. Mr Edwards at the September meeting
2017-07-05 | 2017-08-01 | Quality impact Assessment (QIA)2017-2018 | Mrs Allott agreed to provide a monthly update for the QIPP programme | Mrs Allott | 2017-09-01 |  | Draft circulated as part of August GB information pack. Will be covered as part of QIPP report , on Sept GB Agenda
2017-11-01 | Page 4 | Child & Adolescent Mental Health Services (CAMHS) Section 75 | Mr Edwards asked for typing errors to be edited as legal document | Mr Chambers | 2017-12-01
2017-12-06 | Page 7 | Performance Report | Mrs Firth to take back to Medicines Management team for action | Mrs Firth | 2018-01-01
2017-12-06 | Page 7 | Performance Report | Mrs Firth to look at overall SY&B financial position & report back to GB | Mrs Firth | 2018-01-01
2017-12-06 | Page 9 | Q2 Commissioning Performance Plan | Mr Atkinson to clarify medicines management resource spend and report back to GB | Mr Atkinson | 2018-01-01