## Sheet1
Meeting Date | Ref | Item | Action Required | Lead | Timescale | Status | Update
2017-03-01 | 239/16a | Patient Safety & Quality Assurance Report | Changes in legislation around Deprivation of Libertys guidance (lawful detainment of a patient who lacks capacity) need to be re-iterated to practices. These will be conveyed at PLTC and in the GP Bulletin. | Dr Kitlowski/ Mrs Cassin |  | Amber | message about last changes to go in GP news letter end March/beg April. Paper being drafted for OE outlining main changes expected following last review and Law Commission analysis of possible implications. (28/03/17). Awaiting guidance (3/5/17)
2017-04-01 | 08/17 | Delivery Dashboard | Deep dive into waiting times to be undertaken | Mr Atkinson |  |  | Complete reported in May
2017-06-01 | 07/17 | Delivery Dashboard | More information to be put in the narrative around TRFT A&E performance in future performance reports | Mr Atkinson |  |  | Complete reported in June
2017-06-01 | 07/17 | Delivery Dashboard | Mr Atkinson to include comparison data on the NHS111 service in the Performance Report once available | Mr Atkinson |  |  | Complete
2017-07-05 | 42948 | Performance Reports | Mr Barber requested the rag ratings to be reviewd | Mrs Allott | 2017-10-01 |  | Draft circulated as part of August GB information pack. Will be covered as part of QIPP report , on Sept GB Agenda
2017-07-05 | 42948 | Delivery Dash Board | Mr Atkinson agreed to provide a update on the urgent and Emergency Care Centre | Mr Atkinson | 2017-09-01 |  | Update will be covered in the performance section of the September meeting, report to be prepared following 3 monthsof activity
2017-07-05 | 42917 | Assurance Group | Ms Nutbrown and Ms Hague agreed to attend the Assurance Group meeting to discuss the Risk Regisiter | Mr Nutbrown & Mrs Hague | 2017-10-01 |  | Ms Nutbrown attended the Assurance group meeting on the 27 September 2017
2017-07-05 | 42856 | Chief Officers Report | Mr Edwards asked Mrs Henderson to confirm who from CCG should atttend the official opening of the Urgent and Emergency Care Centre in October | Mr Edwards | 2017-09-01 |  | the offical opening has now been confirmed. Mr Edwards at the September meeting
2017-07-05 | 42948 | Quality impact Assessment (QIA)2017-2018 | Mrs Allott agreed to provide a monthly update for the QIPP programme | Mrs Allott | 2017-09-01 |  | Draft circulated as part of August GB information pack. Will be covered as part of QIPP report , on Sept GB Agenda
2018-01-03 | 04/18 | Draft Minutes of the Governing Body meeting held 1st November 2017 | LH to edit minutes | Mr Edwards | 2018-02-01
2018-01-03 | 06/18 | Primary Care Access | Dr Carlisle to take back to Primary Care Committee to consider how we change our plans to reflect this feedback | Mr Edwards | 2018-02-01
2018-01-03 | 06/18 | Primary Care Access | Mr Edwards to take to next cycle of RCCG planning to inform the next step | Mr Edwards | 2018-02-01
2018-01-03 | 09/18 | Patient Safety & Quality Assurance Report | Mrs Cassin to review CHC information reported to GB to ensure members fully sighted on national reporting requirements. | Mrs Cassin | 2018-02-01
2018-01-03 | 10/18 | Equality & Diversity | Any changes to policies to be submitted and finalised by end of January | Mrs Nutbrown | 2018-01-01
2018-02-07 | 25/18 | ACS Template for EIS&E | GB noted and approved the use of these templates. Mr Edwards asked Mrs Henderson to take the forms back to the appropriate committees to persons cited on the documents. | Mr Edwards | 2018-03-01
2018-02-07 | 27/18 | Improving ambulance Services | Mr Atkinson to find out who represents Rotherham at Huddersfield CCG , what the make-up of the team is and what clinicians are involved and report back at next GB | Mr Atkinson | 2018-03-01
2018-02-07 | 30/18 | Finance & Contracting Performance | Mrs Allott to take back to Stuart Lakin to scope out more ideas | Mrs Allott | 2018-03-01
2018-04-04 | 67/18 | Patient Safety & Quality Assurance Report | Stroke Performance - more detail will be given to pick up raised questions in next GB Report. | Mr Atkinson//Mrs Cassin | 2018-05-01 |  | Detailed information to be taken to AQuA for discussion about data and assurance available
2018-04-04 | 70/18 | Commissioning Plan | Reference the 5 Hospital priorities for HSR to be included in Comm Plan | Mr Atkinson | 2018-05-01
2018-04-04 | 74/18 | Delivery Dashboard | Deep dive into cancer waiting times for May agenda | Mr Atkinson | 2018-05-01
2018-04-04 | 74/18 | Delivery Dashboard | TRFT Performance for ultrasound update | Mr Atkinson | 2018-05-01
2018-04-04 | 74/18 | Delivery Dashboard | Consult Dr Cullen about Public/Confi agenda item - Cancer specialty level information | Mr Edwards | 2018-05-01
2018-05-02 | 90/18 | Action Log |  |  |  |  | stroke performance data shared at AQUA , discussed oversight of detailed information in AQuA and bring the assurance via the AQuA chair lay member to GB for Assurance
2018-06-06 | 112/18 | Delivery Dashboard | Mr Atkinson to incoraporate improving antibiotic prescribing in Delivery Dash Board | Mr Atkinson | 2018-07-01 |  | completed
2018-06-06 | 122/18 | Rothehram AGM | Mr Laidlaw to circulate a Final Flyer with exact timings as confirmation | Mr Laidlaw | 2018-07-01 |  | completed