## GB SUMMARY
QIPP Plan Monitoring Dashboard 2017/18 |  |  | AP5
[7 empty] | Financial Rating |  | Operational Rating |  |  | Key
Area | Scheme | Planned Savings | Year to Date Actuals | Lead GP | Lead Officer | Lead Exec | Year To Date Position | Forecast Outturn Position | Year To Date Position | Forecast Outturn Position
Acute | Reduction in follow-ups where provider is above peer average | -487.783 | -203.2429 | Dr Birks | S Lever | Ian Atkinson | 4 | 4 | 4 | 4 | 1 | 2 | 3 | 4
| Reduce the levels of growth in A&E, assessments and non elective admission activity in line with local trend analysis | -1931.8755 | -522.9481 | Dr Birks | S Lever | " | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4
| Clinical Thresholds - TRFT | -2453.4588 | -455.2745 | Dr Birks | S Lever | " | 1 | 2 | 4 | 4 | 2 | 2 | 1 | 1
| Clinical Thresholds - Other Contracts | -737.6043 | -243.3351 | Dr Birks | S Lever | " | 1 | 2 | 3 | 3 | 1 | 1 | 1 | 4
Narrative on Acute QIPP Schemes:
• Follow-ups – the contract rules are applied and an adjustment is made to reduce the payment for follow ups when they are over the ratios;
• Reducing the levels of growth in A&E, assessments and non elective admission activity in line with local trend analysis is judged to be amber at this stage as there is a slight over-performance at non TRFT trusts £182k and £98k at TRFT. This is forecast to perform to plan for the remaining months but not to pull back the year to date position, therefore this has now changed to amber;
• Clinical Thresholds for all providers are on track operationally but financially red year to date because they are not achieving and amber at year end as the estimate is that these will deliver from July to March but will not pull back the year to date under-achievement, so there will be an under-achievement at year-end of approximately £0.6m.
[7 empty] | Financial Rating |  | Operational Rating
Area | Scheme | Planned Savings | Year to Date Actuals | Lead GP | Lead Officer | Lead Exec | Year To Date Position | Forecast Outturn Position | Year To Date Position | Forecast Outturn Position
Mental Health | Reduction in demand for Ferns | -800 | -800 | Dr Byrnes | K Tufnell | Ian Atkinson | 4 | 4 | 4 | 4 | 1 | 2 | 3 | 4
Narrative on Mental Health Schemes: • Mental Health – this has been agreed and the contract with RDASH reduced to reflect current clinical activity in this area.
[7 empty] | Financial Rating |  | Operational Rating
Area | Scheme | Planned Savings | Year to Date Actuals | Year to Date Actuals | Lead Officer | Lead Exec | Year To Date Position | Forecast Outturn Position | Year To Date Position | Forecast Outturn Position
Prescribing | Rollout of medicines waste reduction programme to all GP Practices | -1400 | -300 | Dr Holden | Stuart Lakin | Wendy Allott | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4
| Branded Generics - switch range of drugs to specific brands at below drug tariff price | -750 | -295 | Dr Holden | Stuart Lakin | " | 2 | 2 | 4 | 4 | 1 | 2 | 3 | 4
| Projects and product switch - introduction of guidelines, switches to more cost effective products etc. | -350 | -133.3333 | Dr Holden | Stuart Lakin | " | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4
| Self management of a range of identified drugs | -151 | -50 | Dr Holden | Stuart Lakin | " | 2 | 2 | 4 | 4 | 2 | 2 | 1 | 1
| Waste reduction scheme, expand into Care Homes | -500 | 0 | Dr Holden | Stuart Lakin | " | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4
Narrative on Prescribing QIPP Schemes: | [12 empty] | 1 | 4
[13 empty] | 1 | 4
Waste Reduction | [12 empty] | 1 | 4
The waste reduction programme has been rolled out to 29 of Rotherham’s 31 practices. There is little likelihood of the remaining practices adopting the scheme in the near future. | [12 empty] | 1 | 4
Savings to date are estimated to be £0.8m. As previously reported there are reductions in paracetamol , emollient , GTN (-18%) usage . Rotherham’s data and promotional material has been at their requested given to Sheffield, Barnsley & Doncaster CCGs . Further savings could be realised if the MMT had the capacity to offer practices more support to: | [12 empty] | 1 | 4
• Increase electronic repeat dispensing practice online ordering | [12 empty] | 1 | 4
• Undertake medicine utilisation reviews | [12 empty] | 1 | 4
• Quantity calculations (does the quantity = the monthly requirement) | [12 empty] | 1 | 4
• Challenging instances where third party ordering is still being practiced. | [12 empty] | 1 | 4
[13 empty] | 1 | 4
Branded Generics | [12 empty] | 1 | 4
The programme was on schedule, but has recently been halted, following NHSE’s latest intervention in category M drug pricing. The impact of the effect of this on market prices needs to be evaluated before further BG switches can be considered. | [12 empty] | 1 | 4
[13 empty] | 1 | 4
Prescribing Projects | [12 empty] | 1 | 4
Programme on schedule no data available | [12 empty] | 1 | 4
[13 empty] | 1 | 4
Self- care | [12 empty] | 1 | 4
Programme launched July 2017 – no data available | [12 empty] | 1 | 4
[13 empty] | 1 | 4
Waste reduction Nursing Homes | [12 empty] | 1 | 4
Scoping project begun, MMT capacity is the rate determining issue. | [12 empty] | 1 | 4
[13 empty] | 1 | 4
[13 empty] | 1 | 4
[13 empty] | 1 | 4
[7 empty] | Financial Rating |  | Operational Rating
Area | Scheme | Planned Savings | Year to Date Actuals | Lead GP | Lead Officer | Lead Exec | Year To Date Position | Forecast Outturn Position | Year To Date Position | Forecast Outturn Position
CHC | Review of CHC cases against frameworks and legislation | -207 | -86.25 | Dr Page | Alun Windle | Sue Cassin | 4 | 4 | 4 | 4 | 2 | 2 | 1 | 1
| Review of assessment tool for determining care packages | -200 | -83.3333 | Dr Page | Alun Windle | Sue Cassin | 4 | 4 | 4 | 4 | 1 | 2 | 3 | 4
| Ongoing clinical review of high cost placement packages | -50 | -20.8333 | Dr Page | Alun Windle | Sue Cassin | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4
| Further development of Personal Health Budgets | -200 | -83.3333 | Dr Page | Alun Windle | Sue Cassin | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 4
Narrative on CHC QIPP Schemes -
• Review of CHC cases against the framework for both Adults and Children, these decisions are facing increased challenge from partner agencies with some being sent to independent agencies for scrutiny - so far all decisions by the CHC service have been upheld. Change in practice has commenced and is working effectively from an operational perspective.
• Joint reviews of high cost placements with the Local Authority for children have been completed. Adults have been agreed in principle for joint reviews to take place however this has not commenced at present therefore is amber financially as the overall CHC plan is in balance at the moment.
• Personal Health Budget development continues and is a rolling programme over the next 2 years therefore is amber financially as the overall CHC plan is in balance at the moment.
[7 empty] | Financial Rating |  | Operational Rating
Area | Scheme | Planned Savings | Year to Date Actuals | Lead GP | Lead Officer | Lead Exec | Year To Date Position | Forecast Outturn Position | Year To Date Position | Forecast Outturn Position
Running Costs / Corporate | Reductions in running costs - various schemes | -200 | -83.3333 | Dr Cullen | Ian Atkinson | C Edwards | 3 | 3 | 3 | 3 | 1 | 2 | 3 | 4
| Slippage on developments | -500 | -500 | Dr Cullen | Ian Atkinson | C Edwards | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4
Narrative on Running Costs / Corporate Schemes: There have been changes to the workforce which has reduced the running costs quantum. The slippage on developments is non recurrent in relates predominantly to the additional running costs attributable to the new Waverley development which will not be live until 2018/19 at the earliest. The funding has been ringfenced for this purpose recurrently.
[7 empty] | Financial Rating |  | Operational Rating
Area | Scheme | Planned Savings | Year to Date Actuals | Lead GP | Lead Officer | Lead Exec | Year To Date Position | Forecasted Outturn Position | Year To Date Position | Forecast Outturn Position
Tariff Efficiency | Tariff Efficiency through prices | -5009 | -2087.0833 | N/A | N/A | N/A | 3 | 3 | 3 | 3
Narrative on Tariff Efficiency: The reductions are inherent within the prices applied through the national tariff rules and agreed via the contracts with providers.