## COVER SHEET
Rotherham CAMHS Local Transformation Plan (LTP) - Action Plan CAMHS LTP Action Plan
RAG STATUS
Action behind target for completion within timescale
Action underway but within timescale
Action completed
Action planned but not started
Re-opened
Closed
| Summary of Key Accountabilities | LTP Plan Element: | Lead
| Promoting Resilience, Prevention and Early Life | Perinatal/0-5 Years | Nigel Parkes
|  | Family Support | Jayne Fitzgerald
|  | Schools | Ruth Fletcher-Brown
|  | Self Harm and Suicide Prevention | Ruth Fletcher-Brown
| Improving Access to Effective Support | New Models of Delivery | Nigel Parkes
|  | Improved Communication and Support | Katie Simpson
SEND
|  | Peer Support | Katie Simpson
|  | Crisis Care | Katie Simpson
|  | Transition | Katie Simpson
| Caring for the most Vulnerable | Most Vulnerable | Nigel Parkes
| To Be Accountable and Transparent | Commissioning Arrangement | Nigel Parkes
|  | Access and Waiting Times | Katie Simpson
|  | Investment in Services | Nigel Parkes
| Developing the Workforce | Workforce | Rebecca Mcalister
| Eating Disorders | Eating Disorders | Katie Simpson
The plan consists of the work which is being monitored as part of the improvement journey, and will be referred to as the CAMHS LTP Action Plan. RAG Status is shown against the actions which indicate whether sufficient progress is being made, i.e. the right amount of progress in the right direction at the right pace.

## 1. Peri 0-5 years
Perinatal 0-5 years
Owner: |  | Nigel Parkes
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
Perinatal/0-5 years
1 | Reduce the incidence and impact of postnatal depression. | 1a Perinatal Mental Health Pathway (Local Priority Scheme 19) | Action Competed - Please see Action Plan V10 |  | RCCG | C
|  | 1b – The current Perinatal Mental Health pathway will be reviewed. (A further review of this pathway may be required later in the year when the expected national guidance is published.) | 21.04.16 Nigel Parkes /Kate Tufnell – Pathway document developed by the Task and Finish group. This is now out for feedback from partners. Initial feedback received has highlighted that: • Further work is required to strengthen the primary care element of the pathway. • Medicine management element – a lot of work has been undertaken to develop this section to ensure that practice is aligned across all elements of the pathway (TRFT, Primary care, RDaSH etc.). • Further work is required to develop and formalise the RDaSH input into the pathway. • The Rotherham element of the pathway needs to be aligned with the new NHS England outreach provision. 01.11.17 Work is ongoing across the STP to look at the individual pathways and also across the area. A bid will be prepared for Wave 2 funding. Pathway develop - Next stage:Amend the pathway in line with comments received 2016/17 contract changes:As part of the 2016/17 Contract negotiations the CCG has agreed some additional investment to enable them to work with RDaSH to increase their input into the pathway. Further work is required to agree the details of the business case for this additional investment. This will be managed through the CCGs 2016/17 Contract Adult Mental Health SDIP process. 08.02.18 Bid for funding submitted. Agreed action closed | 2017-09-01 | Nigel Parkes | G
|  | 1c Formal Pathway sign-off by partners organisation completed | A process and timescale for sign-off by all partner organisations need to be agreed- Sign-off by all organisation needs to be completed 09.05.2017 Nigel Parkes – Initial bid for perinatal funding not successful. Further bid to be prepared in line with STP 01.11.17 See update to 1b | 2017-12-01 | Nigel Parkes | A
|  | 1d Implementation of the Pathway | 08.02.18 Revised current pathway in operation. Looking to put in SYB bid for funding to further develop the pathway. | 2018-03-01 | Nigel Parkes | A
|  | 1e – Agree a mechanism to capture patient / service users feedback to inform the pathway development / evaluation | Action Completed - Please see Action Plan V10 | 2016-02-01 | Nigel Parkes | C
|  | 1f Agree delivery plan with GROW (including timescales) | Action Completed - Please see Action Plan V10 | 2016-03-01 | Nigel Parkes | C
|  | 1g Monitor progress against agreed delivery plan | 09.05.2017 Nigel Parkes – The work was not progressed beyond the development of the initial report. | 2016-07-01 | Nigel Parkes | R
|  | 1h Delivery plan completed | 09.05.2017 Nigel Parkes – The work was not progressed beyond the development of the initial report. | 2016-07-01 | Nigel Parkes | R
|  | 1i Review pathway against new national guidance | 11.04.16 Nigel Parkes – No further guidance published yet. | 2018-03-01 | Nigel Parkes | A
1.1 | Perinatal Mental Health - accredited training | Increase the number of staff who have attended accredited training at TRFT over the next 5 years | Action Competed - Please see Action Plan V10 | 2017-05-01 | Juliette Penney | C
|  |  | Kate Tufnell 09.05.2016 • There are 40 places available on an accredited course for the next 3 years. Rotherham NHS FT has requested 5 places for each year. • The course is currently under development and it is anticipated that it will be ready for either September 2016 or January 2017 subject to validation requirements. • Local Education and Training Board (LETB) for Y&H will fund the 1st year, it is then expected that providers will have to fund places for following years. 08.02.18 NP to forward Action Plan to JPe for update. | Annual next 5 years | Juliette Penney | A
1.2 | Training for Health Visitors | 1.2a - Ensure that Health Visitors continue to receive training around mental Health. Keeping up-to-date and having expert knowledge in practice is referenced within the national service specification 2015-16. | Action Competed - Please see Action Plan V10 08.02.18 NP to forward Action Plan to JPe for update. | 2016-02-01 | Juliette Penney | C
|  | 1.2b Audit of Health Visitor training | 11.10.17 - Nigel Parkes to chose responsible person | 2017-02-01 |  | A
|  | 1.2c - To check with the Health Visiting Clinical Managers about how many have received recent training on Maternal Mental Health and perinatal depression and the current practice system/procedures | Action Completed - Please see Action Plan V10 | 2017-02-01 |  | C
1.3 | Healthy Child Programme (0-5 years) | To check if the update has been seen and/or circulated to health visiting teams across the borough. | Action Completed - Please see Action Plan V10 | 2015-12-01 |  | C
1.4 | Early Intervention for 0-2 year olds | Awaiting further guidance | 31.08.16 Nigel Parkes – Not aware of any progress with these pilots. |  | Nigel Parkes | B
1.5 | Maternal, Perinatel and Early Years Health Services and Parenting Programmes | Links to 1 and perinatal work. |  |  |  | B
1.6 | Better Access to Mental Health Services for Pregnant or Postnatal women | Links to 1 and perinatal work. |  |  | Nigel Parkes | B
Impact, Outcome / Difference made
Evidence Bank |  |  |  |  | Date Received / Ref

## 2. Family Support
Family Support
Owner: |  | Jayne Fitzgerald
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
Family Support
2 | Family Support Service | 2a Develop a ‘Family Support Service’ (Local Priority Scheme 5) to specifically support families who have children and young people who may enter services or who are already in services. This includes areas such as ASD, ADHD, Conduct Disorder and intergenerational aspects. Extra funding will be allocated to this action. | Actions Complete - Please see Action Plan V10 | 2016-03-01 | Jayne Fitzgerald | C
|  | 2b Evaluate the new ‘Family Support Service’ and refine as required. This to include:- • Numbers of families supported. • Outcomes of the work • Positive effect on reducing escalating mental health problems. | 06.05.16 Jayne Fitzgerald – Evaluation of pilot service and setting up including numbers of families supported sent to Nigel April 2016. 08.02.17 Nigel Parkes – Receveing ongoing quarterly reports. Spoke to service about a Young Inspectors review. 05.05.2017 Nigel Parkes – The service supported 69 families (86 children) for the year 2016/17. Extra funding is being allocated for 2017/18 onwards. 01.11.17 As at Quarter 2 of 2017/18 – 93 families have been supported and 62% of those are now members of the Forum. There is close working with services and continuing positive feedback from families. | 2017-12-01 | Nigel Parkes | A
|  |  |  | 2018-12-01 |  | B
|  | 2c Achieve the target that 95% of Young People and Families accessing services from the Rotherham Parents Forum (RPF) will be empowered to independently access support services from The RPF or alternative providers (if appropriate). | 06.05.16 Jayne Fitzgerald – 30.04.16 – 95% of families from pilot have felt empowered to independently access services. |  | Jayne Fitzgerald | A
|  | 2d Review of additional funding for 2017/18 |  | 2018-03-01 | Nigel Parkes | B
Impact, Outcome / Difference made
Evidence Bank |  |  |  |  | Date Received / Ref

## 3. Schools
Schools
Owner: |  | Ruth Fletcher-Brown
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
Schools
3 | School Mental Health and Wellbeing | 3a Implement a pilot for a whole school/college approach in Rotherham. | ACTIONS COMPLETE - Please see Action Plan V10 for detail | 2016-03-01 | Ruth Fletcher-Brown | C
|  | 3b Evaluate the effectiveness of the whole school/college approach. | 08.02.18 Evaluation event undertaken in October 2017. Roll out to commence to schools. The whole school project group continues to meet. | 2017-09-01 | Ruth Fletcher-Brown | G | Red to Green 08.02.18
|  | 3c Further roll out through teach meets | 08.02.18 Evaluation event undertaken in October 2017. Roll out to commence to schools. The whole school project group continues to meet. | 2017-12-01 | Ruth Fletcher-Brown | G | Blue to Green 08.02.18
|  | 3d Rotherham Metropolitan Borough Council (RMBC) is working closely with schools in Rotherham on a project which is looking at developing strategies around collective responsibility for children & young people with social emotional & mental health (SEMH) needs through establishing clusters of schools to work in partnership with health and social care partners. This initiative will specifically target the most vulnerable children. | ACTIONS COMPLETE - Please see Action Plan V20 for detail | 2016-09-01 | Rebecca Mcalister | C
|  | 3f Linking CAMHS locality workers into SMH clusters | 08.02.18 Locality workers are undertaking works across the clusters. | 2017-06-01 | Rebecca Mcalister | G | Red to Green 08.02.18
3.1 | Schools Counselling Strategy/Whole Schools Approach | 3.1 Referenced in Rotherham MAST's whole-school approach paper.Includes the use of a multi-disciplinary team to provide a range of services including counselling, family support and staff in schools. | Actions Complete Please see Action Plan V20 |  | Rebecca Mcalister | C
3.2 | Schools Nurse Training | 3.2a Some changes will be made to staff skill-mix and delivery mechanisms to improve access for Children & Young People and schools. | Actions Complete Please see Action Plan V10 | 2016-03-01 | Rebecca Mcalister | C
|  | 3.2b Overall, there are plans to re-commission the 0-19 pathway incorporating School Nursing, Health Visiting, and other health offers over next 18 months. | Actions Complete Please see Action Plan V20 | 2017-03-01 | Rebecca Mcalister | C
|  | 3.2c Need to clarify what offering in terms of mental health and monitor. | 08.02.18 RM to chase feedback from recently circulated questionaire. | 2018-03-01 | Rebecca Mcalister | B
3.3 | Ofsted - Better Inspection for All | 3.3 Continue to link elements of work as appropriate to the Ofsted judgement Personal development, behaviour and welfare.Link Prevent agenda, Spiritual, Moral, Social and Cultural work and British values to Ofsted judgement Personal development, behaviour and welfare. | Actions Complete Please see Action Plan V10 | 2015-16 | Rebecca Mcalister | C

## 4. Prevention
Prevention
Owner: |  | Ruth Fletcher- Brown
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
QA-1 | Establish the Performance Board to ensure strategic accountability, oversight and governance in respect of quality and performance practice |  | The first meeting of the newly established Progress Board is taking place on the 25 May 2016. Terms of Reference have been drafted to include standing items around performance, quality assurance, CSE and children missing from home and care. | 2016-05-01 | Sue Wilson | completed June 16
QA-2 | Promote coaching conversations (using the GROW model of approach) and reflective practice sessions as an integral part of day to day practice between practitioners, managers and Beyond Auditing Auditors |  | The Beyond Auditing Framework references the use of coaching conversations as an integral part of feedback and practice improvement activity. The first formal session for Auditors, Practice Consultants and the Principal Social Worker in relation to the GROW model took place on 19th May 2016. This is now part of the approach linked to Beyond Auditing | 2016-05-01 | Sarah Hunt | completed June 16
QA-3 | Re-launch the Quality Assurance Framework across the whole of children’s social care services. Remedial action required following evidence challenge in November 2016 |  | Quality Assurance Framework partially complete – including Beyond Auditing Framework (see key action 6 below). Updated Team Manager Audit and supervision tool and Safeguarding Visit Framework complete and Programme under review. Re-launch completed | 2016-06-01 | Vicky Schofield | Completed Sept 2016
QA-4 | Produce a monthly Quality Assurance Framework Overview Report and communicate the findings and recommendations to practitioners, operational managers, strategic and political leaders and partners at team and service meetings plus relevant Boards, including the Improvement Board as required |  | See progress update for key action 3. QA Framework Overview Report on track for production June 2016 in line with the re-launch of the QA Framework. - June audits on hold until after launch of new approach. This is now routinely presented to the monthly performance board. | 2016-06-01 | Vicky Schofield | Completed Oct 2016
Prevention
4 | Mental Health Awareness for Children and Young People | 4aContinue to publicise mental health awareness ‘events’ to promote anti stigma through events, communications and marketing plan. Signed up to by partners. Monitored 6 monthly. | Action Complete Please see Action Plan V10 | Mar 2016 & every 6 months | Ruth Fletcher-Brown | C
|  |  | 07.06.16 – Anti stigma Task & Finish Group being arranged. 17.11.16 Ruth Fletcher Brown - No progress to report 08.02.17 Ruth Fletcher-Brown – Communication leads meet regular – devised own set of campaigns to deiver throughout the year. RFB to liaise with Comms Leads and provide assurancemental health awareness continues to be promoted. | 2016-06-01 | Ruth Fletcher-Brown | C
|  |  | 04.05. 2017 Ruth Fletcher-Brown - Some joint work between RMBC and RCCG Comms. Launch of YP mental health campaign in June 2017 | 2016-12-01 | Ruth Fletcher-Brown | C
|  |  | Time to Talk Mental Health February - Time to Talk day takes place on the first Thursday in February run by Time to Change. Mental Health Awareness Week sometimes in May run by Mental Health Foundation. Suicide Prevention Day 10th September. World Mental Health day 10th October. | 2017-06-01 | Ruth Fletcher-Brown | C
|  |  |  | 2017-12-01 | Ruth Fletcher-Brown | G
|  |  |  | 2018-06-01 |  | B
|  |  |  | 2018-12-01 |  | B
|  | 4b Providers to sign up to anti stigma work. | Action Complete Please see Action Plan V20 | 2016-12-01 | Ruth Fletcher-Brown | C
|  | 4c Promote opprotunities whereschools and colleges can engage in anti stigma work | 26.01.16 Sarah McCall & Ruth Fletcher-Brown - Promotional materials for the MyMindMatters website being provided to all schools with cards for every secondary school pupil in the borough. SENCO meeting in March to be attended to provide information on the website and resources. 01.03.16 Sarah McCall - Safeguarding leads meeting to be attended early March plus promotion as part of Community Strategy launch and promotion at young people’s conference. 31.05.16 RFB – this work is being picked up as part of the whole school approach; learning from the projects will be taken forward to the wider school/college community. Healthwatch also need to be involved around peer mentor scheme 30.09.16 RFB - The wholes schools approach will link in where we have that running (only 6 schools – NP to pick up at LTP review meeting in May 04.05.2017 Ruth Fletcher-Brown - YP mental health campaign to be launched in June 2017 | 2017-06-01 | Ruth Fletcher-Brown | G | Amber to Green 08.02.18
A
|  | 4d Supporting schools/colleges to embed a 'mental health' ethos which provides sustained challenge to stigmatisation. | ACTIONS COMPLETE - Please see Action Plan V20 for detail | 2017-07-01 | RMBC | C
4.1 | Rotherham Mental Health Strategy | 4.1a Rotherham Better Mental Health for All policy | 17.11.16 Ruth Fletcher Brown - workshop held with stakeholders In October to progress this. Strategy out for consultation in Nov/Dec RFB – Strategy is now out for consultation. Commentsback in March. Action plan to be developed by July 2017. 04.05.2017 Ruth Fletcher-Brown - Final stratgey goes to H&WBB in May 2017 | 2017-07-01 | Ruth Fletcher-Brown | C
|  | 4.1b Development of the strategy. | Signed off |  | Ruth Fletcher-Brown | C
|  | 4.1c Development of Action Plan. | Signed off |  | Ruth Fletcher-Brown | C
|  | 4.1d Implementation of the plan. | Ongoing |  | Ruth Fletcher-Brown | G | Amber to Green 08.02.18
|  | 4.1e Review Mental Health Strategy | 08.02.17 RFB to provide date of the review of the Mental Health Strategy 2017-20 | 2018-07-01 | Ruth Fletcher-Brown | B
|  |  |  | 2019-07-01 |  | B
4.2 | Self Harm and Suicide Prevention | 4.2a Delivery of actions in the Rotherham Suicide and Self Harm Action Plan April 2016- December 2018. | Action Complete - Please see Action Plan V15 | 2016-03-01 | Ruth Fletcher-Brown | C
|  | 4.2b Develop action plan from April 2016 to December 2018 | Action Complete Please see Action Plan V21 | 2016-04-01 | Ruth Fletcher-Brown | C
|  | 4.2c Delivery of actions in the plan to end March 2017 |  | 2017-06-01 | Ruth Fletcher-Brown | R
|  |  |  | 2017-12-01 |  | B
|  |  |  | 2018-06-01 |  | B
|  |  |  | 2018-12-01 |  | B
|  | 4.2d Provide a self-harm prevention and support model (Priority Scheme 20) | 03.10 update to be provided following meeting this week 11.10.17 Ruth Fletcher Brown to update the wording and provide a completion date | 01/09/2017 (TBC) Oct - Dec 18 | Ruth Fletcher-Brown | A
|  | 4.2e Co-production of the model with children and young people | 03.10 update to be provided following meeting this week 11.10.17 Ruth Fletcher Brown to update the wording and provide a completion date 08.02.18 Implemented in a co-produced way | 01/09/2017 (TBC) Oct -Dec 18 | Ruth Fletcher-Brown | A
|  | 4.2f Implement model |  | 01/09/2017 (TBC) April 18 | Ruth Fletcher-Brown | A
|  | 4.2g Evaluate Model |  | 01.07.2018 | Ruth Fletcher-Brown | B
4.3 | Prevention Self Help |  |  | 2018-10-01

## 5. New Models of Del
New Models of Delivery
Owner: |  | Nigel Parkes
Key actions to address key judgements: |  |  | Progress in this Reporting Period | By When | Action Owner | BRAG
New Models of Delivery
5 | Single Point of Access | Develop the RDaSH CAMHS Duty Team into a true Single Point of Access (SPA). See 7.1a Investigate the option of 'One-stop-shop’ services. These should also include advocacy services, be locality based and work for all, even the most vulnerable. See 5.5 Both SPA and ‘One-stop-shop-services’ should be able to initially support Children & Young People including when in a crisis.
5.1 | One point of contact for a wide range of universal services to access a team of children and young people’s mental health professionals for advice, consultation, assessment and onward referral. | 5.1a Develop the RDaSH CAMHS Duty Team into a true Single Point of Access (SPA) (Local Priority Scheme 13) which will also provide advice on, and signposting to, other services which RDaSH don’t provide such as those provided by RMBC and other organisations. | 10.03.16- RDaSH SPA lead identified. Meetings arranged to explore further the principles of the one-stop approach to single point of access and a multi-agency approach- ‘No wrong door’. 01.04.16 Barbara Murray- SPA lead to commence in post mid-April 2016, staff identified to work within this area. Initial SPA meeting held to discuss processes within RDaSH. 06.05.16 Katie Simpson - Meeting planned for 13.05.16 with David McWilliams re SPA development and links with EH. 10.03.16- RDaSH SPA lead identified. Meetings arranged to explore further the principles of the one-stop approach to single point of access and a multi-agency approach- ‘No wrong door’. 01.04.16 Barbara Murray- SPA lead to commence in post mid-April 2016, staff identified to work within this area. Initial SPA meeting held to discuss processes within RDaSH. 06.05.16 Katie Simpson - Meeting planned for 13.05.16 with David McWilliams re SPA development and links with EH. 03.06.2016 Katie Simpson – SPA team in a live position, working closely with the Intensive Support Team. Systems and processes are being worked up. Positive meeting held with Early Help to progress the co-location and joint working with CAMHS. Proposed action is to hold a workshop with the CAMHS SPA team and the EH team, to process map how CAMHS need a SPA to function, overlay this with how the EH functions and merge the two, working through some live referrals. 12.08.2016 Katie Simpson - First workshop with Early Help held 04.08.2016. Identified possible future processes. Both teams have actions to review and work up and a further workshop will be held in September. Expect to pilot launch from October. 13.09.16 Nigel Parkes – RDaSH CAMHS SPA and RMBC Early Help meet weekly to discuss the appropriateness of referrals. Further meetings ongoing to discuss the development of a combined CAMHS SPA and Early Help Service. 14.12.2016 CAMHS Contract & Performance Meeting - On track for transfer of CAMHS staff to Early Help hub on 17 January 2017. 18.11.2016 Katie Simpson – Due to staff long term sickness within the CAMHS SPA team, leaving the team short staff the pilot of the SPA with Early Help has been delayed and is expected to being in January 2017. In the interim, one SPA practitioner is meeting with the EH team at a weekly consultation and case discussion slot, this appears to be working well and has improved communication and partnership working between the two agencies 11.01.2017 CAMHS Contract & Performance Meeting - GP provided an update on the Single Point of Access Team. The team are still on track for transfer to the Early Help hub on 17 January 2017, but it’s not clear if appropriate communications have been sent out. NP to pick with PT. 08.02.17 CAMHS Contract & Performance Meeting – Barbara Murray confirmed that alternative, more effective ways of working are being considered by CAMHS in light of the new structure which may impact on the transfer. Paul Theaker co-ordinating meeting to discuss way forward. 05.05.2017 Katie Simpson– to be reviewed in line with the development of the SPA with Early Help 01.11.17The CAMHS SPA is working well and has improved access and response times for all requests for support. The model of consultation and advice offered through the SPA continues to develop. The team are still working closely with Early Help to drive forward an integrated front door; the team continue to meet with the Early Help team on a weekly basis to discuss referrals. | 2016-09-01 | Katie Simpson | C
|  | 5.1b Ensure that the SPA makes it easier for patients & parents to navigate and access services, including the option of self-referral into the SPA by patients and parents. | Katie Simpson – to be reviewed in line with the development of the SPA with Early Help 01.11.17 Self-referral continues to be an option through the SPA. The offer of consultation and advice through the SPA has improved the service offer, ensuring that professionals have easy access to timely support, guidance on cases, thus meaning that young people don’t end up with unnecessary referrals into the service. | 2017-04-01 | Katie Simpson | C
|  | 5.1c Evaluate the effectiveness of the SPA. | 11.10.17 Barbara Murray to chase. 01.11.17 Work is underway, to be competed by end of December 2017 17.01.18 JP advised to hold with this until the move within SPA occurs, KS to handover/follow-up 08.02.18 Feedback required reguarding the evaluation and on going changes. | 2017-09-01 | Katie Simpson | A
|  | 5.1d Scope out integration of the SPA with the Early Help Hub | The team are still working closely with Early Help to drive forward an integrated front door; the team continue to meet with the Early Help team on a weekly basis to discuss referrals. |  | Katie Simpson | A
5.2 | Early Help Strategy | 5.2a Ensure that other stakeholders link into the early help teams across Rotherham to deliver consistent messages around early help. | Actions Complete - Please see Action Plan V10 | 2015-12-01 | Rebecca Mcalister | C
|  | 5.2b RDaSH to create clear links through locality workers to RMBC Early Help Teams | Actions Complete - Please see Action Plan V10 |  | Rebecca Mcalister | C
|  | 5.2c Review impact of Early Help Strategy | 04.05.2017 Paul Theaker to undertake work in May 2017 06.06.2017 Ruth Fletcherr-Brown to check with Paul Theaker 11/10/17 Karla Capstick to notify Rebecca Maclaister when evaluation has been completed The development of the Early Help Service is described in the Early Help Strategy as 3 distinct phases. Phase 1 to eastablish the service by March 2017 has been completed but phase 2 to re-design the Service by March 2018 is currently on hold. It is anticipated that this may not begin unitl Autumn 2018 - | 01/12/2016- Autumn 2018 | Rebecca Mcalister | A
|  |  | 08.02.17 Review the impact of the mental health elements of the Early Help Strategy. | 2017-12-01 |  | B
|  |  |  | 2018-12-01 |  | B
5.3 | Initial Risk Assessments | Continue as usual practice. 5.3a RDaSH to ensure that all Children & Young People accessing services are given a FACE risk assessment. The numbers of patients having the risk assessment against all patients referred in to the service should be reported on as part of the normal KPI reporting. | Actions Complete - Please see Action Plan V20 |  | Katie Simpson | C
|  | 5.3b 100% of children will have a FACE (Functional Analysis of Care Environments) risk assessment | 19.10.16 - Currently working up Children’s FACE risk assessment which will be user friendly for clinicians i.e. child’s history will be automatically populated into risk assessment and automatic review reminders generated. 18.11.2016 Katie Simpson – work continues on the development of an improved briefer FACE risk assessment for use specifically within CAMHS. In the interim, we are undertaking weekly data quality checking on completion of FACE Risk Assessments 11.01.2017 CAMHS Contract & Performance Meeting - GP reported that figures are now improving and there is a live assessment window in place for clinicians to access. To be discussed further at the February meeting. 08.02.17 CAMHS Contract & Performance Meeting – Barbara Murray confirmed that the live window provides easier access to information which supports the FACE risk assessment process. 05.05.2017 Katie Simpson – work continues to support staff with the completion of the FACE risk assessment and data quality to ensure reporting is accurate. 01.11.2017 Significant improvements have been and continue to be made with FACE Risk Assessment Compliance. See CAMHS Performance Report. | 2017-03-01 | Katie Simpson | A
| Prompt decision-making about who can best meet the child/young person’s needs (including targeted or specialist services, voluntary sector youth services and counselling services). | See 5.1a | Actions Complete - Please See Action Plan V10 | 2016-03-01 | Katie Simpson | C
| Young people and parents are able to self-refer into the single point of access. | As 5.1a Self-Referral will be an option | Action Complete - Please see Action Plan V12 |  |  | C
5.4 | Provide a key role for the voluntary and community sector to encourage an increase in the number of one-stop shop services, based in the community. | Undertake a scoping exercise to understand how one-stop-shops can be developed in Rotherham. These should be appropriate for all areas, cultures & languages. They should take a Holistic approach and utilise a ‘universal screening tool’. They should also ‘Support’ & ‘Direct’ to other services as appropriate. |  | 2018-09-01 | Nigel Parkes | C
5.5 | Children’s advocacy services | 5.5a The following action is proposed for 2015/16:-Immediate acknowledgement of the existing advocacy role for YP through funding this work for the remainder of Yr. 1 | Actions Complete - Please see Action Plan V10 | 2016-03-01 | Healthwatch | C
|  | 5.5b Review of Children’s Advocacy service | 06.12.2016 Nigel Parkes – Quarterly meetings are taking place between RCCG and HealthWatch. A full review will take place in Q4 of 2016/17. 06.06.17 Nigel Parkes to provide an update. | 2017-05-01 | Nigel Parkes | A
|  | 5.5c In future years:-Ensuring that advocacy for CYP is picked up in a more sustainable way in years 2-5 through building on the current work. Extra funding will be allocated to this action. | 05.05.2017 Nigel Parkes – HealthWatch advocacy service will be reviewed at the end of quarter 1, 2017/18 | 2017-03-01 | Nigel Parkes | A
|  | 5.5d Further evaluation |  | 2017-12-01 |  | B
5.6 | Meeting a Child/Young Person's Needs | See 5.1a | Action Complete - Please see Action Plan V10 | 2016-03-01 | Katie Simpson | C
5.7 | Self-Referral into Single Point of Access | See 5.1a Self-referral will be an option | Action complete - Please see Action Plan V12 |  | Katie Simpson | C
5.8 | Assessment Tool |  |  |  |  | A
5.9 | Development of Emotional Wellbeing and Mental Health Services With input from C&YP and Families/ Carers | 5.9a Scope out current engagement across Rotherham and identify gaps against best practice. Extra funding will be allocated to this action 24.04.16 Nigel Parkes – This relates to local priority scheme 9 in the LTP. | Action Complete Pease see Action Plan V12 | 2016-02-01 | Nigel Parkes | C
|  | 5.9b Propose an engagement strategy including training requirements resulting from the ‘Practical Participation’ work. The output will be a Good practice engagement plan/report for engaging with Children & Young People & families | 09.06.16 Nigel Parkes – Requirement for RDASH to take forward the recommendations included in the 2016/17 Service Development & Improvement Plan (SDIP). 05.05.2017 Katie Simpson – work required to pull together a formalised strategy . Work has been undertaken to engage with children, parents and partners, although further work is required to take this forward and improve consistency. 17.01.18 NP requested AC provide an update on this which describes how to take this forward. 08.02.18 RDaSH to take forward in a number of ways including direct working and joint working with VAR, Health Watch and Parent Carers Forum Rotherham CAMHS is undertaking various work streams to actively engage with children & young people. This has included; meetings with Young Inspectors, a ‘Different But Equal’ Young Persons Event, The Rotherham Show, and World Mental Health Day in October 2017 Further work is ongoing through a Young Peoples Voice and Influence Group which was established in November 2017. This meets monthly to discuss the facilities and services offered by Rotherham CAMHS and how these can be improved and be more relevant to the needs of children and young people. Initial discussions have covered ‘transition’ from CAMHS to adult mental health services or to other supportive services. There are plans to for further events that focus on transitions for young people moving on from CAMHS throughout 2018. | 2016-12-01 | Katie Simpson | G | Changed from Amber to Green 08.02.18
|  | 5.9c Assess the impact of engagement of the new model over 2016/17 2018/19 |  | 01/06/2017 change to Sept 18 |  | R
|  | 5.9d Commissioners and Providers work with the Youth Cabinet to deliver their Manifesto aims. | Action Complete Please see Action Plan V12 | 2016-04-01 | Ruth Fletcher-Brown | G
|  |  | 06.06.17 Update from Sarah Belamy required 11.10.17 Nigel Parkes had met with the Youth Cabinet and plans were outlined 16.11.17 - Nigel Parkes & Ruth Fletcher-Brown attended Youth Cabinet Manifesto Launch. | 2017-03-01 | Ruth Fletcher-Brown | C
|  |  |  | 2018-11-01 | Ruth Fletcher-Brown | B
|  | 5.9e All contracted provision to have clear Voice and Influence approaches outlined and monitored. | 13.09. Nigel Parkes – ‘Voice and Influence’ requirements to be part of the revised CAMHS service specification 07.12.2016 Nigel Parkes – RDaSH has developed an action plan to improve the input of C&YP and parents/carers into service improvement / delivery etc. It has also developed a new Patient Engagement Strategy. 05.05.2017 Nigel Parkes – No further update 08.02.2018 The scope of this work will be picked up through the CAMHS Strategy and Performance Meeting with all generic CAMHS Services | 2016-04-01 | Nigel Parkes | A
5.1 | Online Support for Children, Young People and Parents/Carers | 5.10a Development of the my mind matters website |  |  |  | A
Impact, Outcome / Difference made
Evidence Bank |  |  |  |  | Date Received / Ref

## 6. Improved Commun and Supp
Improved Communication And Support
Owner: |  | Katie Simpson
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
MASH-1 | Ensure there is high level engagement from all partners (including VCS) at the MASH Senior Management Steering Group to ensure full multi agency accountability and ownership |  | Action re-opened 9th Jan 2017 (previously closed Sept 2016) A full review of partnership engagement from all agencies is to be undertaken, governed through the MASH Management Steering Group. There is now a clear expectation of the Role of the Probation service within First Response therefore a local working agreement will be developed and agreed to support this. In addition RDaSH representation within the First Response needs to be formalised. This action has been closed March 2017 and replaced with action MASH-11 | 2017-05-01 | Ian Thomas | Closed Mar 2017
Improved Communication & Support
6 | Improving communications and referrals, for example, local mental health commissioners and providers should consider assigning a named point of contact in specialist children and young people’s mental health services for behaviour and GP practices; and schools should consider assigning a named lead on mental health issues. | 6.a RCCG to continue to work with RDaSH to ensure that communication continues to improve and undertake an annual survey monkey to confirm this. | 09.05.16 – Survey Monkey will be undertaken now in June/July following final reconfiguration of the service. 31.08.16 Nigel Parkes – Survey monkey will be undertaken in March 2017 and yearly thereafter. 01.11.17 It is planned to undertake a new survey in the next few weeks. The details are being worked through. 01.11.17 It is planned to undertake a new survey in the next few weeks. The details are being worked through. | Mar-17 Mar-18 | Nigel Parkes | A
|  |  |  | Mar-18 Mar-19 | Nigel Parkes | B
|  | 6.b RCCG & RDaSH to continue to update the CAMHS Top Tips and DOS documents. | 13.01.16 N Parkes – Documents circulated for comment Dec 2015. 11.04.16 Nigel Parkes – Top Tips updated & will be signed off at the CAMHS Strategy & Partnership meeting - 11th May. DOS still being amended following RMBC IYSS changes. 31.08.16 Nigel Parkes – Sign off delayed, awaiting reconfiguration of Early Help services. Will go to CAMHS Strategy & Partnership meeting 12 Oct 2016. 05.05.2017 Nigel Parkes – Top tips and Directory of Services updated and signed off in November 2016 | 2017-04-01 | Nigel Parkes | C
|  |  | CAMHS Top Tips and DOS documents have been updated recently. October 2017 | 2018-04-01 | Nigel Parkes | G | Changed from Blue to green 08.02.18
|  | 6.c Identify a named RDASH CAMHS lead for other children's services e.g. Fostering, Residential, Youth Services, Youth Offending etc. | Actions Complete Please See Action Plan V21 | 2018-04-01 | Katie Simpson | C
6.1 | Locality Worker Model | 6.1a RDaSH to implement the Locality Worker model and create working links with all GP localities, schools/colleges and key services in each area. This to include both telephone and face to face links and delivery of community services as appropriate. | Action Complete Please see Action Plan V12 | 2015-12-01 | Nigel Parkes | C
|  | This links to the SEMH work outlined in 2 above. |  |  | Nigel Parkes | G
|  | 6.1b RDaSH to undertake an audit of activity undertaken away from Kimberworth. Results will follow after the audit (not in January). | Action Complete Please see Action Plan V12 | 2016-01-01 | Nigel Parkes | C
|  | 6.1c RDaSH to provide monthly data relating to activity away from Kimberworth | Action Complete Please see Action Plan V12 |  | Katie Simpson | C
|  | 6.1d Evaluate the ‘Locality Worker Model’ through an internal RDaSH evaluation and external stake holders | 03.06.2016 – Katie Simpson – Evaluation proposed to begin September 16 once the locality workers have been in post 6 months. 19.10.2016 – Evaluation to take place March 2017 08.02.17 CAMHS Contract & Performance Meeting – Barbara Murray confirmed that the consultation and evaluation process is expected to be complete by the end of May 2017. 05.05.2017 Katie Simpson – Evaluation underway. 06.06.2017 Katie Simpson KS – New locality worker in post. Delay RDaSH internal evaluation until July. 01.11.2017 Draft document prepared, awaiting some data to update and finalise. Expected Nov-17 17.01.18 KS informed this is completed but needs to be finalised 08.02.17 Completed and finalised | 2018-03-01 | Katie Simpson | G | Changed from Amber to Green 08.02.18
6.2 | ASD Support for Schools/Colleges | 6.2a Develop specific ASD support for schools/colleges, including training for staff (which will need to be ongoing to account for staff turnover). This could include having a named Autism advocate for each school/college. |  | 2017-03-01 | Rebecca McCallister | C
|  | 6.2b Review of models of delivery for support around ASD. This to apply both pre and post diagnosis. | Actions Complete Please See Action Plan V20 | 2016-09-01 | Paul Theaker | C
6.3 | Post diagnosis ASD Support Service for Families | 6.3a Implement family and patient based post diagnosis ASD support. This is a joint project with RMBC and will complement the schools based support provided by the Autism Communication Team. Extra funding will be allocated to this action. 24.04.16 Nigel Parkes – This relates to local priority scheme 3 in the LTP. | Actions Complete Please see Action Plan V25 | 2016-03-01 | Caroline Wheatley | C
|  | 6.3b The ASD support service to achieve the KPI target of 15 referrals per month for the 3 months from January 2016 to March 2016. An outcome measure will then be developed for 2016/17 | Actions Complete Please see Action Plan V16 | 2016-03-01 | Caroline Wheatley | C
|  | 6.3c Evaluate the new family & patient based ASD support service. | 04.05.17 Lianne Morewood – data collected, report to be completed by 30th June 2017 01.11.2017 Action completed report sent to NP September 2017 Quarterly reports ongoing regarding KPI's Sensory project report and summary sent to NP September 2017 | 2017-06-01 | Caroline Wheatley | C
|  | 6.3d Further evaluation of ASD support service | 08.02.18 Quarterly meeting regulates the service evaluation. | 2017-12-01 | Caroline Wheatley | G | 08.02.18 Green from Blue
|  |  |  | 2018-06-01 | Caroline Wheatley | B
6.4 | Schools Named Mental Health Lead | 6.4a Investigate the options of schools/colleges having a named mental health lead whether this is extending the existing roles of the SENCOs or the Healthy Schools Co-ordinator or School Nurses or another option. Review existing models and/or providers to establish most effective representation model for schools, including a learning community/cluster model which acts as conduit between specific schools and CAMHS. | Action Complete - Please see Action Plan V17 | 2017-07-01 | Rebecca Mcalister | C
|  | 6.4b Develop ‘Wrap around care’ for children in the school setting | Action Complete - Please see Action Plan V17 |  |  | C
G
6.5 | Communication with Patients, Families and Referrers | 6.5a RDaSH CAMHS to undertake a quarterly audit of written and other communications with patients, families and referrers. Any issues highlighted will then be addressed on an ongoing basis. | Action Complete - Please see Action Plan V26 | Mar, Jun,Sept, Dec 2016 | Katie Simpson | C
|  |  | Action Complete Please see Action Plan V26 | 2016-08-01 | Katie Simpson | C
G
|  |  | Action Complete Please see Action Plan V26 | 2017-02-01 | Katie Simpson | C
Impact, Outcome / Difference made
Evidence Bank |  |  |  |  | Date Received / Ref

## 7. SEND
SEND
Owner: |  | Paul Theaker
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
SEND
7 | SEND | Scope out the current links between CAMHS and the RDaSH Learning Disability service, with particular emphasis on transition and the 18 to 25 year old cohort of patients. This also, links to LD FastTrack model? | Action Complete - Please see Action Plan V15 | 2016-06-01 | Katie Simpson | C
7.1 | There is a strategic link between children’s mental health services and services for children and young people with special educational needs and disabilities (SEND) | 7.1a RDaSH CAMHS to establish a SEND lead. | Action Complete - Please see Action Plan V12 | 2015-10-01 | Katie Simpson | C
|  | 7.1b RCCG, RMBC & RDaSH to undertake a scoping exercise to understand what actions still need to be undertaken. | 10.02.16 Paul Theaker - No CAHMS input at the minute. ASD draft strategy in place. 02.03.16 Nigel Parkes – A meeting has been organised to discuss this and specifically RDaSH CAMHS input into the SEND agenda. 11.04.16 Nigel Parkes – Meeting held 8th April to discuss joint working. 17.11.16 Paul Theaker - RDaSH CAMHS responsibilities being clarified through the development of the SEND HUB at Kimberworth. Workshop with Senior Leaders in early December. 04.05.2017 Paul Theaker - RDaSH CAMHS fully involved in the development of the SEND Hub. | 2015-12-01 | Rebecca Mcalister | C
|  | 7.1c RDaSH to be more actively involved in the SEND hub and processes. | Oct 2017 - Katie to provide update following meeting on 03/10/17. 17.01.18 AC is involved with this and attends monthly meetings. It was agreed this now green | 2017-11-01 | Katie Simpson | G | Red to Green 17.01.18
7.2 | Mental Health Professional Co-ordinated Assessment and Planning - EHC Plan | 7.2a Undertake scoping exercise to understand if this currently happens. | Action Complete Please See Action Plan V26 | 2015-12-01 | Katie Simpson | C
|  | 7.2b Stakeholders to further develop SEND hub | 06.06.17 Stakeholders to further develop SEND HUB – Paula to become lead. 08.02.18 SEND Hub is established. |  |  | G | 08.02.18 Amber to Green
Impact, Outcome / Difference made
Evidence Bank |  |  |  |  | Date Received / Ref

## 8. Peer Supp
Peer Support
Owner: |  | Katie Simpson
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
Peer Support
8 | Peer Support Schemes | 8 Evaluate the current use of peer support networks to understand how best to further develop these. | 26.01.16 Ongoing. Alison Courtney to link in with the peer support workers and establish an audit tool to evaluate. Feedback end March 2016 29.02.16 Claire Strachan: we will need to agree who will lead on this now and how the data is extracted and when. 10.03.16 Barbara Murray - the peer support workers continue to work with young people transitioning into adult services. Additional work is being undertaken in schools and colleges regarding mental health awareness with positive effect. 06.05.2016 Katie Simpson – requires further discussion within RDaSH to determine a lead for the evaluation and scope of review to be completed. 03.06.2016 Katie Simpson – BM has asked for clarity of expectations - is this broader than just RDaSH? Will work up a questionnaire that can be sent to those children and young people who the peer support workers have worked with over the last 12 months to gain feedback on their experience of the peer support workers. 12.08.2016 Katie Simpson – Peer Support Worker Evaluation data report requested via organisational process, timescale TBC. This will provide information on client experience of peer support workers for last 12 months. 18.11.2016 Katie Simpson – Data available from Silver link is insufficient to support a robust evaluation. Therefore a questionnaire has been sent to all young people who have worked with a peer support worker in the last 12 months. Feedback will support the evaluation and development of the service moving forward. 14.12.2016 CAMHS Contract & Performance Meeting - Questionnaires circulated to patients who have accessed a peer support worker in the last 12 months. Final report expected in January 2017. 11.01.2017 CAMHS Contract & Performance Meeting - Final report to be brought to the February meeting. 08.02.17 CAMHS Contract & Performance Meeting – Barabara Murray confirmed that there has been limited feedback received which needs to be collated. In light of the low response rate CAMHS are considering alternative ways of requesting the information. Final report to be brought to the March meeting. RDASH update required 06.06.17 Barbara Murray - RDASH report complete, meeting Friday to finalise 01.11.17 Report completed and shared with commissioners in June. Development of the Peer Support Worker role is underway in line with the developments outlined in the Transition Benchmarking Toolkit. Need to understand the wider Peer Support Worker offer as per action 8.2 to identify how the CAMHS PSWs interface with this. 01.11.17 Rotherham Parent Cares Forum offer extensive peer support networks through their organisation, including; drop-in sessions, face to face meetings, telephone, facebook and twitter. | 2016-03-01 | Katie Simpson | C
8.1 | Peer support schemes should be led and designed by children and young people or by parents or carers, with careful professional support to reduce and manage risk both to peer mentors and the young people and families they are involved with. | 8.1 RDaSH to work with children & young people, parents and carers to further develop peer support schemes. This links to 2 above. | Action Complete - Please see Action Plan V15 | 2016-09-01 | Katie Simpson
8.2 | Peer Support Audits | 8.2 RMBC & RDaSH to work with education and third sector partners to audit what is currently available. | 10.03.16 Locality leads will support the development of the peer support model within areas once identified and work plans configured. 06.05.2016 Katie Simpson – As above 30.10.17 - No Update - Handover from Paul Theaker not provided. Requires guidance 03.06.2016 Katie Simpson – still be worked up. 18.11.2016 Katie Simpson – Please can we have some clarity on this action, this seems wider than RDASH – we are auditing and evaluating as above are unclear on what actions other partners are undertaking. 07.012.2016 Nigel Parkes – RDaSH actions covered in 11a above. RMBC to evaluate what Peer Support is available in schools / colleges and third sector partners. 20.01.17 Nigel Parkes – Discussed at Schools Interface meeting on 19.01.17 and agreed to focus on peer supportamongst schools. Potential teach meet approach. 06.06.17 RDaSH report complete –meeting with Kate RMBC update required 08.02.18 Rebecca Maclister to provide feedback regarding peer support from a recently circulated Education Survey. |  | Rebecca Mcalister | A
Impact, Outcome / Difference made
Evidence Bank |  |  |  |  | Date Received / Ref

## 9. Crisis Care
Crisis Care
Owner: |  | Katie Simpson
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
CSE-1 | Develop a mechanism for reporting the CSE scorecard highlights and exceptions to the Performance Board. Formally signed off a evidence challenge in October 2016 |  | The CSE Score Card has been refreshed and the report finalised and will form part of the Monthly CSE Profile report. | 2016-06-01 | Sue Wilson | Completed Sept 2016 and signed off by evidence challenge
CSE-2 | Undertake a review of the preventative actions in relation staff suffering from stress within the Evolve Team and follow up on recommendations for promoting staff resilience and wellbeing |  | There is a Staff Welfare Policy in place which includes additional monthly clinical supervision and access to bespoke counselling from therapist specialising in sexual violence and the impact on staff. All staff is aware of how to access the service. Additional Team Managers have been put into place increasing capacity and supervision is now timely. Staff can take up counselling on an individual basis when required. This action is now business as usual as part of all social work teams and Corporate RMBC staff HR protocols and procedures. | 2016-11-01 | Vicky Schofield | Closed January 2017
CSE-3 | Enhance the skills and ability of staff to communicate directly with children & young people (whose first language is not English) as part of the practitioner’s toolkit. |  | Communicating with children and young people whose first language is not English, there has been a significant activity in regards to this action: Three learning events which included - a Roma Awareness day open to all social workers - Bespoke awareness training for Evolve social workers and managers provided by Clifton Learning Project Roma Specialist worker. - 2 days training for all CSE Champions and Evolve Social Workers provided by Apna Haq with a focus on assessing the needs and working with BME perpetrators of CSE and non-abusing family members and their children and victims of CSE from within the BME community. 2 m/a residential activities aimed at young people in the Rom Community Under development is a practitioners CSE toolkit which will include a section on developing and maintaining Cultural Competence. This work is now business as usual and this action to be closed | 2016-07-01 | Lynn McIntosh | Completed Sept 2016
Crisis Care
9 | Ensuring the support and intervention for young people being planned in the Mental Health Crisis Care Concordat is implemented. | All partners involved in the Crisis Care Concordat to continue to work together to fully implement the Crisis Concordat action plan. | 25.11.15 Claire Strachan - First review of C&YPMHS Liaison post submitted to RCCG. New policy for care of children and young people in acute hospital wards ratified and promotes use of a first contact crisis card. 27.01.16 Claire Strachan - a CAMHS 136 flow chart has been agreed for RDaSH aligned to SY Police removal of police cells as a place of safety. This has been shared with SY Police and circulated within RDaSH. 13.09.16 Nigel Parkes – Crisis Care Concordat meetings re-instigated 07.12.2016 Nigel Parkes – CCC meeting organised for 7th February 2017. 01.11.17 A meeting took place on the 5th October. Further meetings are planned going forward. | Ongoing | Nigel Parkes | A
9.1 | All Ages Crisis Service (including Children and Young People) | 9.1a RDaSH to implement an ‘All Ages’ Crisis service, which links together the out of hours ‘Access’ service and the ‘in-hours’ Liaison service to provide a 24/7 service with a 1 hour response time to A & E. Extra funding will be allocated to this action. | 03.06.2016 Katie Simpson - Intensive Support pathway now live. Appropriate cases now handed over. Working collaboratively with Paediatric Nurse Liaison to respond to urgent and crisis. Criteria being drafted for the intensive support service – expected for the end of June. Work being undertaken with Adult services to support the CAMHS service to move to 8am-8pm with Adult services covering 8pm-8am, OOHs provision will continue until all appropriate training and system and processes have been planned through with adult services. 12.08.2016 Katie Simpson – Team now fully live and accepting referrals and undertaking assessments and interventions as per criteria. Each team member is currently working with a caseload of 12. Work continues on transitioning the team to an 8-8 service. Work to be completed on “launch” of service with other agencies. 13.09.16 Nigel Parkes - Continued meetings with adults around clinical aspects. Driving for October but 30 day consultation so may be Nov/Dec. 19.10.16 Nigel Parkes – Discussions ongoing regarding how each RDaSH area can have a Crisis Service 18.11.2016 Katie Simpson – BM has a meeting scheduled with the Adult Crisis Team to further discuss and identify training requirements. A consultation paper will be sent to the January Trust Staff Council from which the formal 30 day consultation can begin. 14.12.2016 CAMHS Contract & Performance Meeting - Now working in care groups. CH re-submitting papers to Trust Staff Council in January 2017. Hope to run service in shadow form from March 2017. 08.02.17 CAMHS Contract & Performance Meeting – Discussed at the Trust Staff Council meeting and an action generated to develop a training plan and ensure pathways are efficient. Barbara Murray confirmed that the service is on track for June implementation. 05.05.2017 Katie Simpson– Work continues with AMH To progress this development. Work is underway to identify staff training needs and develop appropriate training package. 01.11.2017 A sucessful bid was submitted for £50K funding to support the development of the All Age Crisis Service. The bid will allow for backfill to release staff for training and development. | 01/03/2016 ( Revised to March 2018) | Katie Simpson | A
|  | 9.1b Evaluation of the ‘All Ages’ Crisis service. This to include consultation with C & YP/Parents/Carers on the effectiveness of the new model. This to also demonstrate effective working with the new ED development at TRFT |  | 01/09/2017 (Revised to Sept 2018) | Katie Simpson | B
|  | 9.1c RDaSH to achieve the KPI target of 95% of Children & Young People in Crisis seen within 1 hours in TRFT A & E Every young person presenting with self-harm or crisis seen within 2 hours regardless of setting | 05.05.2017 Katie Simpson – to be reviewed and implemented in line with new 17-18 schedule reporting | 2016-03-01 | Katie Simpson | A
9.2 | Out of Hours Mental Health Service | See 9.1a above | ACTIONS COMPLETE – Please see Action Plan V10 for detail |  | Katie Simpson | C
21.04.16 Nigel Parkes – This relates to local priority scheme 2 in the LTP
CSE-9 | Complete the renovation of the Eric Mann’s accommodation to support effective and cohesive joint working and promote the Evolve team identity |  | Social workers, Health and PACE workers have all now moved to Eric Manns. Police moved in on the 20th June and formal open day held. Feedback so far from staff and visitors has been excellent, this included the visit from the SoS on the 8th September, members have also visited and provided excellent feedback. | 2016-06-01 | Lynn McIntosh | Completed Sept 2016
CSE-10 | Complex and high profile CSE multi agency enquiries to have an appropriate multi agency command and governance structure in place following the Silver (operational) and Gold (strategic) model of approach |  | There is now one single Gold Group for CSE matters chaired by ACC Rowley. This group has met once and AD CSE Operations has briefed ACC Rowley on current operations | 2016-09-01 | Gary Ridgway | Completed Sept 2016
CSE-11 | All complex and high profile CSE multi agency enquiries need to include a multi-agency learning event in order to share learning and practice to inform on-going practice |  | Operation Clover college of policing learning event documentation now received into SYP. Op Marshall Gold ( ACC Rowley) is considering dissemination. Operation Taffeta learning document complete and circulated to all interested parties. Chair of RSCB will make decision on publishing of document on RSCB website. OP Marshall Gold (ACC Rowley) is reviewing document to consider options for publication. Operation Scorpio independent review team have completed 5 days of review and are currently producing a learning document. Hot de-brief delivered to RSCB executive board on the 13/10/16. Full De-brief of learning to be presented to DCS and ACC Rowley 31/10/16. No current operations underway that have not been subject to multi-agency learning event. Intention is to conduct learning event following injunction applications to high court. This is now business usual. | 2016-09-01 | Gary Ridgway | Completed Oct 2016
CSE-12 | Re-invigorate the monthly CSE Steering Group membership and established as part of routine business |  | CSE steering group dates are now set and attendees agreed. The First meeting has gone ahead and the will be held regularly Second meeting went ahead but attendees agreed that multi agency working has matured to the extent that the need for this type of ‘problem solving’ group is no longer required as issues can be dealt with through current business practices. | 2016-06-01 | Gary Ridgway | Completed Sept 2016
9.4 | Transition Pathways out of inpatient care | See 9.1a above and 9.5a below. This includes an 'All-ages' liaison service.
9.5 | Clear evidence-based pathways for community-based care. | 9.5a Develop an ‘Intensive Community Support Service (Local Priority Scheme 1). This will form part of the ‘All Ages’ Crisis Service outlined in 12.1.1 above. Extra funding will be allocated to this action. 21.04.16 Nigel Parkes – This relates to local priority scheme 1 in the LTP. | ACTIONS COMPLETE – Please see Action Plan V16 for detail | 2016-03-01 | RDaSH | C
|  | 9.5b Evaluation of the ‘Intensive Community Support Service’. Links to 19.2.1 below. | 14.12.2016 CAMHS Contract & Performance Meeting - The service specification is being worked up and flow charts will be developed for each area. 11.01.2017 CAMHS Contract & Performance Meeting - Service specification shared with NP, but requires more detail. GP to feedback to Darren Brierley. 08.02.17 CAMHS Contract & Performance Meeting – Katie Simpson confirmed that monthly reporting commenced from the end of January 2017 and will form part of the overall quality report shared with commissioners. 01.11.2017 Evaluation underway, expected end of Nov 2017 17.01.18 An update was requested on this. 08.02.18 This will be picked-up at the forthcoming Quality Visit due to take place on 21.02.18 | 01/12/2016 Nov 2017 | Katie Simpson | A
|  | 9.5c Further evaluation and development of the ‘Enhanced Community Support Service’, dependent on the status of inpatient services and commissioning responsibilities (links to funding streams). | 17.01.18 KS to check with Jackie. Agreed action can go blue. linked to 9.5b | 2017-12-01 | Katie Simpson | B | Turned Blue from Red 17.01.18
|  | 9.5d Investigate the option of a ‘place of safety’ which will help to avoid admissions to Tier 4 services and Paediatric Wards and enable earlier step-down once admitted. | 13.09.16 Nigel Parkes – Potential application for capital funding to establish a ‘place of safety’ 07.12.2016 Nigel Parkes – Capital funding bid not able to be progressed. Suggest extend deadline. Now see 9.11b | 2017-09-01 | Nigel Parkes | A
|  | 9.5e RDaSH to achieve the KPI target of a reduction (% TBC) in average bed-days of children & young people admitted to a Tier 4 bed. Data provided by NHSE |  | 2018-03-01 | Katie Simpson | B
|  | 9.5f Review the current multi-agency pathways and develop family friendly versions. | 07.12.2016 Nigel Parkes – Initial meeting took place 28th October 2016. Nigel Parkes to provide update 06.06.17 Paul Theaker to provide an update 03.10 Rebecca McCallister to discuss with the Different but Equal Board to understand what format children and young people would want to seethe pathways in. | 2017-03-01 | Rebecca Mcalister | A
9.6 | Investment in effective targeted and specialist community provision. | See 9.5b above.
9.7 | Clear pathways for young people leaving inpatient care | 9.7 RDaSH to regularly meet with NHS England to evaluate how the pathways are working. This links to 13.1 above, which will facilitate earlier discharge from Inpatient facilitie | ACTION COMEPLETE – Please see Action Plan V10 for detail |  | RDaSH | G
9.8 | Access Assessments for CYP with learning difficulties | 9.8 RCCG to liaise with NHS England to understand if this process is working and agree roles & responsibilities. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-01-01 | RCCG | G
9.9 | CTR Guidance | 9.9 RCCG to liaise with NHS England to clarify the status of recent CTR guidance to understand if this process is working and agree roles & responsibilities. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-01-01 | Nigel Parkes | G
9.1 | Discharge Plans for CYP | See 9.5a above | ACTIONS COMPLETE – Please see Action Plan V10 for detail |  |  | G
9.11 | Place of Safety | 9.11a RCCG and RMBC to work together to assess the option of a 'Place of Safety' as an alternative to The Rotherham NHS Foundation Trust (TRFT) Paediatric ward.
|  | 911b RCCG to continue discussions with other local CCGs concerning a potential regional option for a ‘Place of Safety’. | 11.04.16 Nigel Parkes – meeting held 6th April with South York’s Commissioners & Providers to discuss pathway. Further clarity required re. Capital funding. 13.09.16 Nigel Parkes – Sheffield CCG submitted bid for a regional place of safety. 07.12.2016 Nigel Parkes – SCCG successful with bid for ‘Place of Safety’. Potential opportunity for access by Rotherham patients in second phase. 05.05.2017 Nigel Parkes – No further developments 13.02.18 - Nigel Parkes - A project has started with a South Yorkshire group of CCGs to look at Crisis provision and 'Place of Safety' will be one of the areas of discussion. | 2016-03-01 | Nigel Parkes | A
9.12 | 136 Suite | 9.12a RDaSH to develop reporting relating to the ‘Intensive Community Support Service’ outlined in 13.1 above. This to include; support provided against provision and the use of the 136 suite for under 18 year olds, admission avoidance to Tier 4, etc. | 06.05.2016 Katie Simpson – To be reviewed as part of the development of this pathway model. Internal meeting to be held 12.05.2016. Proposed meeting for discussion with Commissioners 25.05.2016. 03.06.2016 – Katie Simpson – update as per 12.1 07.12.2016 Nigel Parkes – RCCG and RDaSH in ongoing discussions regarding the reporting. 08.02.17 CAMHS Contract & Performance Meeting – Nigel Parkes coordinating meeting between footprint commissioners, CAMHS and NHS England to discuss Tier 4 provision. 01.11.2017 Work underway on the development of reporting in line with the KPI and service specification requirements as per of the new EPS SystemOne developments - expected to go live 30 November 2017. 17.01.18 BM informed a pathway has been identified on SystmOne. AR attending a meeting regarding this. | 01/03/2016 30/11/2017 | Katie Simpson | A
9.13 | CQC Assessments of places of safety | See 9.5d above.
Impact, Outcome / Difference made
Evidence Bank |  |  |  |  | Date Received / Ref

## 10. Transition
TRANSITION
Owner: |  | Katie Simpson
Key actions to address key judgements: |  |  | Progress in this Reporting Period | By When | Action Owner | BRAG
PLO-1 | Undertake a Legal Service Peer Review to assure quality, strengthen practice and a deliver value for money service |  | Uma Mehta (London Borough of Islington, legal services) has been stepped down in order for Lincolnshire Legal Services to lead the peer review. A date has yet to be agreed although an improvement partnership set up meeting is due to take place between Rotherham - Lincolnshire on 8th June 2016. Peer Review has now taken place and was led by Rebecca Andrews and actions are being addressed. | 2016-07-01 | Lincolnshire Legal Services | Completed Sept 2016
Transition
10 | Transition to adult services | 10a Use the results of the scoping exercise around transition and the transition specification template to develop a CAMHS transition specification | 02.03.16 – Nigel Parkes – A transition CQUIN is being discussed with RDaSH for 2016/17. 07.06.16 Nigel Parkes – Transition CQUIN in place. 13.09.16 Nigel Parkes – CAMHS transition specification still to be developed 07.12.2016 Nigel Parkes – CAMHS transition specification being prepared. 05.05.2017 Nigel Parkes – Preparation of Transition Specification delayed 01.11.17 Further delay in fianlisitng specification due to lack of capacity Nigel to review Section 10.1 & 10.2 | 2016-03-01 | Nigel Parkes | G | 08.02.18 Amber to Green
|  | 10b Implement the CAMHS Transition Specification. | 03.06.2016 Katie Simpson - RDaSH transition protocol currently under review in line with National specification guidance. 05.05.2017 Katie Simpson – Transition policy updated in line with national guidance. Benchmarking complete. Service is working as part of the Yorkshire & Humber Clinical Network working group on the development of standardised transition tools including appropriate questionnaires. Unsure whether the specification has been received into the service? 01.11.2017 Benchmarking complete with action plan in place to achieve areas requiring developments. No specification received from Commissioners to implement. 17.01.18 JP Suggested having a policy on the RDaSH website rather than a specification 08.02.18 Reviewed 08.17 RDaSH introduced CAMHS Transition Policy | 2017-03-01 | Katie Simpson | G | 08.02.18 Amber to Green
A
|  | 10c Confirm that the process followed by RDaSH for transition is working and is effective for the patients and their families. A National CQUIN for transition from CAMHS to adult mental health services will be in place for 2017/18 and 2018/19. KPI target - Percentage of children & young people experiencing a good transition to Adult services. | 07.12.2016 Nigel Parkes – RDaSH has completed a self-assessment template for transition and are preparing an evidence base and action plan. 08.02.18 Action now closed | 2016-12-01 | Katie Simpson | G | 08.02.18 Amber to Green
|  |  | As above 17.01.18 AC has disccused earlier and suggestion to use the reflection of the 2018-20 CQUIN | 2017-03-01 | Katie Simpson | A
A
A
A
|  | 10d Develop a service for supporting C&YP who do not transition to adult services but who need support. This relates to local Priority scheme 18 and will receive new funding in 2017/18 | 05.05.2017 Nigel Parkes – Initial meeting taking place between RCCG and RMBC to agree way forward. VAR have produced an initial scoping report and this will be used to inform future meetings and development work. 01.11.17 Work still ongoing around the implementaion of the Social Prescribing service. Transitions events now being proposed for the remainder of 2017/18 | 2017-04-01 | Nigel Parkes | A
|  |  | 08.02.18 Review Priority Scheme | 2018-09-01 | Nigel Parkes | A
10.1 | Continuity of Care | 10.1a RDaSH CAMHS and Adult services to work together to improve the process of transition. | 07.03.16 Nigel Parkes – CCG currently negotiating RDASH CQUIN cover transition. 06.05.2016 Katie Simpson - Robust transition policy in place. Rotherham CQUIN around transitions- there is a meeting on Monday 9th May to develop further. 03.06.2016 – Katie Simpson -Working closely with adult services to improve transition, including the review of the transition policy. Requirement to re clarify the role of the care coordinator in the transition process. Making improvements to MDT approach to discuss transition cases. Identifying a link a person in adult services. 14.12.2016 CAMHS Contract & Performance Meeting - NP awaiting feedback from Barbara Murray on NHS England’s transition toolkit. Deadline Friday 16th December 2017. Katie Simpson to follow up. 11.01.2017 CAMHS Contract & Performance Meeting (Nigel Parkes) - The transition toolkit has now been submitted to NHS England. The RDaSH transition policy has been refreshed and now includes CAMHS transition. CH is working closely with Care Group Directors to ensure transition is seamless as possible. Transition is also being taken forward through CQUIN for 2017/18. 05.05.2017 Katie Simpson – no further update, work continues as outlined above. 11.11.2017 A Transiition Doctor working collaboratively across both services has been appointed. A monthly transitions meeting is now in place and well attended. The services have submitted a successful business case to fund a 6 month Transition Care Coordinator that will care coordinate and interface between CAMHS and AMHS. | 2016-03-01 | Katie Simpson | C
|  | 10.1a - i RDaSH to review the impact of the Transition Doctor and Care Coordinator. |  | 2018-06-01 | Katie Simpson | B
|  | 10.1b RCCG and RDaSH to discuss the long term objective of an ‘all age’ service which therefore doesn’t require transition. | 14.12.2016 CAMHS Contract & Performance Meeting - CH working closely with Adults services to refine the transition process. This is an ongoing piece of work which is supported by the Place Base model. 11.01.2017 CAMHS Contract & Performance Meeting - IJ outlined that it is no longer a long term intention of RDaSH to move to an ‘all age’ service, which will incorporate CAMHS services into the combined Adult/OP services. NP felt this had not been outlined to the CCG and agreed to pick this up with Kate Tufnell. RCCG to provide update 08.02.18 Item covered earlier | 2016-09-01 | Nigel Parkes | G | 08.02.18 Amber to Green
|  | 10.1c RDaSH CAMHS to provide 6 monthly transition reports. | 27.01.16 Claire Strachan - the service does capture electronic detail regarding the number of cases requiring transition, those with a transition plan in place and those who have completed transition in quarter: this does require some manual data entry and monitoring and the PSW’s review the Transition plan monitor report. CS has provided the current information re process to NP to establish the level of any enhanced reporting required. 29.02.16 Claire Strachan - no further update 06.05.2016 Katie Simpson - There is data on the reportal which is used for identifying transitions, but further work required to produce a meaningful report. 03.06.2016 Katie Simpson – Report updated in line with CQUIN reporting 10.10.16 Nigel Parkes - Picked up through transition reports. 05.05.2017 Katie Simpson – addressed through the CQUIN reporting. 17.01.18 RADaSH CAMHS provide 6 monthly transition reports. AC to discuss within the team and provide the report. 08.02.18 Regular reports through CQUIN | 2016-03-01 | Katie Simpson | G | 08.02.17 Amber to Green
Impact, Outcome / Difference made:
Evidence Bank |  |  |  |  | Date Received / Ref

## 11. Most Vulnerable
Most Vulnerable
Owner: |  | Nigel Parkes
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
Most Vulnerable
11 | Health Inequality Access and Outcomes | 11a All stakeholders to work together to assess how the pathways work for the most vulnerable and ‘hard to reach’ groups. | 13.09.16 Nigel Parkes – Proposing to start a piece of work in March 2017. This is being picked up through the Raising Aspirations meetings, but only for Looked After Children | 2017-09-01 | Nigel Parkes | A
Completed Sept 2016
Completed Sept 2016
|  | 11b Consult with LGBT groups around emotional wellbeing and mental health issues. This will include:- • Developing an action plan around promoting mental well-being. • Actions within the plan may include; - Programmes to enable young people to understand about the importance of looking after themselves, as well as developing strategies which may enable them to cope better with stress and anxiety. - Development of resources and training packages for teachers and other practitioners on how their role can promote the emotional well-being of LGBT young people. - To deliver an LGBT workshop within the Youth Cabinet’s Self Help conference in March 2016. This is supported by extra funding in 2015/16 21.04.16 Nigel Parkes – This relates to local priority scheme 7 in the LTP. | ACTION COMPLETE – Please see Action Plan V16 for detail |  | RDASH | C
|  | 11c Review the implementation of the actions including assessing against the KPI for a minimum of 28 young people to attend residential/workshops and 10 Youth Work Sessions delivered. | ACTION COMPLETE – Please see Action Plan V17 for detail | 2016-03-01 | Rebecca McCalister | C
|  | 11d Assess the impact of the action plan. | RMBC update required 06.06.17 Paul Theaker to provide update 30/10/16 RDaSH to lead 11/10/17 Rebecca Mcalister to pick up Evaluation of the pilot was included in action 11c) In terms of long term impact it is reported that: Staff awareness was raised. Staff knowledge and confidence has also been raised. As new young people come forward for support the staff are equipped to support them. | 2016-09-01 | RDASH | C
11.1 | Care Plans for Young People |  | ACTION COMPLETE – Please see Action Plan V12 for detail |  | RDaSH | C
Completed Oct 2016
11.2 | Multi-agency Teams For Referal of Vulnerable Children and Young People | 11.2a Stakeholders to work together to understand how the Early Help teams, RDaSH CAMHS SPA, Youthstart and other access points to services need to interface to ensure that referrals are made to the most appropriate services. Links to 1.5 and 7 above. | Actions picked up under 1.5 and 7 above.
Closed January 2017
|  | 11.2b Undertake a piece of work to understand if the criteria for referrals should extend beyond ‘clinical diagnosis’ and includes presenting needs and professional or family concerns. | 05.05.2017 Katie Simpson – scope of work needs to be determined and developed in line with the developments with multiagency working, and integration of the SPA with Early Help 01.11.2017 Model of consultation and advice offered through SPA and locality workers, which allows consideration of wider issues impacting on emotional and mental health and wellbeing. Further work to be undertaken in line with the developments of an integrated front door with Early Help. 08.02.18 This work is under advice consultation work. | 2017-03-01 | Katie Simpson | G | 08.02.18 Amber to Green
11.3 | Mental Health Assessments | 11.3a Confirm that all commissioned services include sensitive enquiry about neglect, violence and abuse. This needs to also include child to parent violence, e.g. relating to adoption. Also, diversion from the criminal justice system. Also, consider that this should apply to all young children and not just those 16 and above. | 27.01.16 Claire Strachan - the CAMHS Business Division has agreed that a staff development session will be offered to embed this in practice. 11.02.16 Sara Graham - As a schools commissioned service, Rotherham MAST adheres to individual school safeguarding policies and procedures, but this routinely involves sensitive enquiry when work with a child or young person of any age gives rise to the possibility or suspicion of neglect, violence and/or abuse. 15.02.16 Frankie Hibbard - We are going to look at our assessments and make sure we are covering this and if not we will develop a new one. 17.02.16 Sara Whittaker - Social work assessments routinely explores these aspects and considers impact on mental health – services are sought to assist CYP in this situation. Sara Whittaker to consider asking Kelly white/ Shazana Jamal at RMBC for further information. 29.02.16 Claire Strachan - has developed a package for the training of staff in Doncaster and 3 sessions are planned for March for Doncaster CAMHS and Project 3 staff. This can then be rolled out to Rotherham CAMHS staff. 01.04.16 Barbara Murray- initial sessions delivered by Claire Strachan, these will be transferred across other services as identified above 27.04.16 Katie Simpson – Initial feedback from staff that further training is not required. Audit being undertaken across division to understand whether training is required or whether reporting processes need to be changed. 03.06.2016 Katie Simpson – Audit is in progress, expected end of June. Training / changes in practice will be explored following the completion of this audit. 14.12.2016 CAMHS Contract & Performance Meeting - An audit was undertaken across the division and a training package is being rolled out in Doncaster in Jan/Feb. Katie Simpson hopes to adopt the training programme for Rotherham. 05.05.2017 Katie Simpson – Training has been delayed due to sickness. Training dates to be rearranged. 17.01.18 Update required. | Dec-15 June-18 | Nigel Parkes | R
|  | 11.3b RCCG to liaise with the Criminal Justice System to understand how children & young people diverted and the role of RDaSH services. | 05.05.2017 Nigel Parkes – No further update 11/10/17 Nigel Parkes to chase Date extension from Mar-17 to Nov-17 | 2017-11-01 | Nigel Parkes | A
|  | 11.3c RCCG to confirm that RDaSH and other relevant services receive referrals from the SARC service in Sheffield | 05.05.2017 Nigel Parkes – No further update 11.010.17 Nigel Parkes to provide an update 01.11.17 Pathway confirmed from SARC service to CAMHS, including Paediatrics. | 2017-03-01 | Nigel Parkes | C
11.4 | Sexual Abuse and/or Exploitation Assessment and Referral Including CSE | 11.4a RCCG to confirm that there are clear referral routes to the local SARC service. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2015-12-01 | Nigel Parkes | C
Complete Nov 16
|  | 11.4b Enhance the current CSE support to Children & Young People. KPI target - Enhanced service established Extra funding will be allocated to this action. 21.04.16 Nigel Parkes – This relates to local priority scheme 10 in the LTP. | ACTIONS COMPLETE – Please see Action Plan V25 for detail | 2015-12-01 | Nigel Parkes | C
|  | 11.4c Young people affected by CSE will be triaged within 24 hours for urgency. If the referral is deemed urgent the CYP will be seen within 24 hours. | ACTIONS COMPLETE – Please see Action Plan V26 for detail | 2017-03-01 | Nigel Parkes | C
|  | 11.5d Evaluation of the Enhanced CSE support |  | 2017-06-01 | Nigel Parkes | R
|  | 11.4e Implement a post abuse service model to ensure that there is a priority referral into CAMHS where there are mental health issues. This to include opportunities for quick access back into services at a later stage if appropriate. | Sara Whittaker / Gary Pickles to provide update PT speak to commissioner 06.06.2017 Update from Paul Theaker required 11.10.17 Nigel Parkes to add Trauma to this section 01.11.17 This will now incorporate C&YP affected by Trauma. A meeting has been arranged for 30th November to scope out a Trauma pathway. 13.02.18 Nigel Parkes - the meeting took place and a follow-up meeting is being arranged. | 2016-09-01 | Nigel Parkes | A
11.5 | Multi-Agencey Safeguarding Hubs (MASH) | Confirm RDaSH representation on the MASH and look at options if that isn’t the case. | ACTION COMPLETE – Please see Action Plan V12 for detail | 2015-12-01 | Katie Simpson | C
Complete June 16
Completed Oct 2016
Completed Sept 2016
Closed January 2017
11.6 | Support Services for Vulnerable Young People with Multiple and Completx Needs | 11.6a The LAACTT team will provide a range of therapeutic advice, consultation and interventions to reduce current waiting lists. This is supported by extra funding in 2015/16. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-03-01 | Sara Whittaker | C
|  | 11.6b To offer one off / brief therapeutic advice and consultation to carers/parents/ staff as part of duty / brief intervention services. At least one case per week – 12 - 16 – 20 cases addressed. (Up to 40 if two per week). | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-03-01 | Sara Whittaker | C
|  | 11.6c To offer therapeutic interventions to ten children/families – up to 16 dyadic sessions each, approximately weekly. This will reduce waiting times, and enable children to be seen for direct work when needed. (3 or 4 families for 3 days each week). | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-03-01 | Sara Whittaker | C
|  | 11.6d To develop and pilot a group for young people on social skills, regulation and relevant matters – in line with development of NICE guidance on attachment. (One day per week). | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-03-01 | Sara Whittaker | C
11.7 | Intergration of Services CAMHS & LAC | 11.7a Assess whether there is a clear lead professional arrangement currently in place for patients being picked up by the LAACTT Team and RDaSH CAMHS. If not, then implement such a system | ACTION COMPLETE – Please see Action Plan V12 for detail | 2016-12-01 | Katie Simpson | C
|  | 11.7b Provide further non-recurrent investment in services for LAACTT. | ACTION COMPLETE – Please see Action Plan V12 for detail | 2016-12-01 | Nigel Parkes | C
|  | 11.7c RDaSH will develop a process for prioritising LAAC and Care Leavers entering the CAMHS or Adult services. | ACTION COMPLETE – Please see Action Plan V12 for detail | 2016-12-01 | Katie Simpson | C
|  | 11.7d RDASH to implement a 3 month pilot to prioritise the treatment of LAC in the RDaSH services | ACTION COMPLETE – Please see Action Plan V12 for detail | 2016-12-01 | Katie Simpson | C
|  | 11.7e Evaluation of the pilot | 05.05.2017 Katie Simpson – Service Manager pulling together the evaluation paper 01.11.2017 Evaluation of pilot completed and shared with all parties. | 2016-12-01 | Katie Simpson | C
11.8 | Trauma and Mental Health Awareness Training | 11.8a RDaSH to demonstrate how they improve the skills of staff and make them more aware of the impact of trauma on mental health and on the wider use of appropriate evidence-based interventions. | 09.06.16 Nigel Parkes – RCCG to discuss with RDASH that action needs to be taken 07.12.2016 Nigel Parkes – Proposed action updated for clarity. 05.05.2017 Katie Simpson– delayed, needs to be worked up. Need clarity on what commissioner expectations are. | Sept-16 Sept-18 | Rebecca Mcalister | A
|  | 11.8b RMBC to extend this awareness raising to residential home staff & schools staff. | 26.01.16 Sarah McCall & Ruth Fletcher-Brown - 3 Youth Mental Health First Aid courses and 3 Suicide Prevention courses held. Plus brief intervention courses on suicide prevention held for residential home staff. 26.01.2016 Sara Whittaker - LAACTT offer consultation, advice and training in the residential homes and in the leaving care sectors as possible – including therapeutic care planning, and training and client based therapeutic consultations – including round self-harm issues. (LAACTT). 04.05.2017 Ruth Fletcher-Brown - 4 SafeTalk suicide prevention training sessions were held in March 2017 which were attended in the main by people working with/caring for young people. | 2016-09-01 | RMBC | A
11.9 | Teams Specilising In Supporting Vulnerable Children and Young People e.g LAAC | No Action
11.1 | Specilist Service for Mental Health or Neurodevelopmental Difficulties | No Action
11.11 | Consultation and Liaision Teams | RDaSH to liaise with the LAACTT and Youth Justice System to ensure that support can be provided to children & young people with highly complex needs as required. | ACTION COMPLETE – Please see Action Plan V12 for detail | 2016-03-01 | Katie Simpson | C
11.12 | Specilist Point of Reference For Mental Health Services | RDaSH to identify a senior clinician to link with the LAACTT. | ACTION COMPLETE – Please see Action Plan V12 for detail | 2015-12-01 | Katie Simpson | C
11.13 | Joint Working with Youth Junstice System | RDaSH to ensure that there is effective joint working with the Youth Justice System. |  | 2018-03-01 | Katie Simpson | B
11.14 | Mental Health Practitioners Embedded in Early Help and Other Teams | Ensure that RDaSH mental health workers are embedded in, or link into Early Help and other Teams, through the locality approach. Links to 1.5b and 22a above. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2015-12-01 | Katie Simpson | C
11.15 | CAMHS Team Understanding of Most 'At Risk' C&YP | RDaSH to ensure that the CAMHS service has awareness of the fact that some children & young people are the most excluded from society, such as those involved in gangs, those who are homeless or sexually exploited, looked-after children and/or those in contact with the youth justice system. And that this may mean they require different approaches to the norm. | 18.11.2016 Katie Simpson – Revised pathway structure including CSE pathway and improved interagency working. 07.12.2016 Nigel Parkes – RDaSH CAMHS now prioritises LAC for assessment and a pilot has also started whereby LAC are also prioritised for treatment. 05.05.2017 Katie Simpson – LAC pilot continues as well as improvements to interacgency working. All children in contact with the service receive a comprehensive and holistic assessment and individualised care based on their needs. 01.11.2017 All children in contact with the service receive a comprehensive and holistic assessment and individualised care based on their needs. Work is undertaken collaboratively with relevant individuals in the child’s care network. | 2016-09-01 | Katie Simpson | C
Impact, Outcome / Difference made:
Evidence Bank |  |  |  |  | Date Received / Ref

## 12. Commissioning Arrang
Commissioning Arrangments
Owner: |  | Nigel Parkes
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
LAC2-1 | Ensure all children in care (aged 2 to 18th birthday) have a high quality Personal Education Plan (PEP) in place so that they receive appropriate support and achieve their full potential |  | Compulsory age for PEP extended from 3 to 18, will be 2 in July 2016. Improved processes linking virtual school to social care, PEPS now recording "voice", the quality of PEPS continues to improve, PDRs for the team are targeting good or better PEPs for all, training has now started with the Designated Teachers | 2016-07-01 | Lorraine Dale | Completed Sept 2016
LAC2-2 | Establish a strong governance model for the Virtual School and establish a Management Steering Group to provide scrutiny, challenge and support and drive up the educational achievements of children in care |  | Agreement reached with Deputy Leader regarding: timing of meetings of a Virtual School Governing body, initial draft terms of reference have been revised , potential membership, reporting lines and agenda. The first meeting of the Governing Body is 16th June, chaired by the Deputy Leader with Deputy Director, AD Education & Skills and Head Teachers from all phases as members. A foster care is currently being sought | 2016-07-01 | Lorraine Dale | Completed Sept 2016
Commissioning Arrangements
12 | Lead commissioning arrangements for children and young people's mental health and wellbeing services | 12a RCCG and RMBC to continue discussions around co-commissioning options. |  | Ongoing | Nigel Parkes | A
|  | 12b The ‘CAMHS’ Strategy will be reflected in the local CAMHS transformation plan. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2015-10-01 | Nigel Parkes | C
|  | 12c The local JSNA to be regularly updated to ensure that service developments are driven by current needs. | See 12.7 below
|  | 12d The ‘Needs Analysis’ which informed the Emotional Wellbeing and Mental Health Strategy development in 2014 will also be updated on a regular (yearly) basis. | 17.11.16 Paul Theaker - Information currently being collated. 04.05.2017 Paul Theaker - Needs Analaysis finalised | 2016-12-01 | Ruth Fletcher-Brown | G | 08.02.18 Red to Green
|  |  | 08.02.18 Update needs analysis. Strategy and Performance meeting for sign-off | 2017-12-01 |  | A | 08.02.18 Red to Amber
12.1 | Lead Accountable Commissioning Body For Evidenced-based Care | 12.1a The CAMHS Strategy & Partnership Group will oversee the local CAMHS Transformation Plan and link into the Health & Wellbeing Board. | ACTION COMPLETE – Please see Action Plan V12 for detail | Ongoing | ALL | C
12.2 | Identifiable Budget for Children's Mental Health Services | See action 12.1 above.
12.3 | Local Plan For Child Mental Health Services | This is covered by the CAMHS LTP.
12.4 | Local Plan Linked to Health & Wellbeing Strategy | The Health & Wellbeing Board will sign off the Local Transformation Plan. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2015-10-01 | Nigel Parkes | C
12.5 | Health & Wellbeing Board (H&WB) Oversight | See 12.4 above.
12.6 | Engagement of Schools and Others not Linking inot the H&WB | Ensure that MIND, MAST and RMBC Educational Psychologists feed into the development of the Transformation Plan. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2015-10-01 | Nigel Parkes | C
12.7 | Ensuring the JSNA and Health & Wellbeing Strategies address issues effectively & comprehensivley | RMBC and RCCG to ensure that the JSNA is up to date and that both the JSNA and Health & Wellbeing Strategy reflect the mental health needs of children, Young people and their families. | 04.02.16 Nigel Parkes – There is a process within RMBC for updating the JSNA, but the responsibility for the CAMHS section lies with the CCG. Further discussion is needed concerning how to take this forward. 31.03.16 SM – process in place to review JSNA twice yearly. Work ongoing but complete for the purpose of this plan. 17.11.16 Paul Theaker - Needs analysis will inform the JSNA. 04.05.2017 Paul Theaker - Needs Analaysis finalised 30.10.17 - The CAMHS needs analysis has been updated and recommendations will be identified as a partnership group. This action links with 13.0 around collecting and incorporating data on the wider CAMHS services inot the JSNA 08.02.18 Awaiting sign off | 2018-05-01 | Rebecca Mcalister | A
12.8 | Long Term Tracking of CAMHS & Adult Patients | RCCG to work with RDaSH (CAMHS and Adult services) to understand what data is available and could be collected in future. | 22.12.15 Included by Sarah McCall 07.12.2016 Nigel Parkes – Data to support this work is not routinely collected. To include in CAMHS SDIP. 05.05.2017 Nigel Parkes – Further discussions to be undertaken between RCCG &RDASH 01.11.17 This data is still not routinely collected. RDaSH is moving to a new IT system and this will be picked up again. 08.02.18 Nigel Parkes to discuss with Dianne Graham as not currently doing. | 2016-09-01 | Nigel Parkes | A
12.9 | Co-Commissioning of Community & Inpatients Services | 12.9a RCCG and NHS England to work closely to manage this process of transferring of inpatient commissioning responsibility. | 09.06.16 Nigel Parkes – Some initial discussions have taken place relating to Amber Lodge service in Sheffield, but so far not for the specific Tier 4 inpatient services. 19.10.16 Nigel Parkes – RCCG has met with NHSE to discuss co-commissioning of services in the future. A workshop will be organised in December and joint plans should be produced by December 2016. 07.12.2016 Nigel Parkes – Workshop with NHSE scheduled for the 12th December 2016. 05.05.2017 Nigel Parkes – Drafy Yorkshire & Humber joint commissioning plan prepared. 01.11.17There has been some transfer of responsibilities through the move of Amber Lodge commissioning responsibility from NHS England to South Yorkshire & Bassetlaw CCGs. Unsure of further proposed changes at this stage. | 2016-03-01 | Nigel Parkes | A
|  | 12.9b Continue to hold monthly meetings to discuss Tier 4/Complex patients to ensure that commissioners work together in the interests of these patients. | 25.11.15 C Strachan - the service continues to provide information and attend the Tier 4 meeting. 13.1.16 Nigel Parkes – meetings now being held quarterly but with continuing monthly updates of the spreadsheet. 09.06.16 Nigel Parkes – Monthly updates of the spreadsheet are continuing. 05.05.2017 Nigel Parkes – Reporting is now managed through RDASH monthly reporting. Work being implemented to look at ‘At Risk’ patients in Rotherham. 01.11.17 There has been some transfer of responsibilities through the move of Amber Lodge commissioning responsibility from NHS England to South Yorkshire & Bassetlaw CCGs. Unsure of further proposed changes at this stage. | Ongoing | Nigel Parkes | A
|  | 12.9c Develop collaborative commissioning networks with Health and Justice/specialised commissioners to develop pathways for the services they directly commission | 01.11.17 Some work undertaken across all commissioners, but more focused work will be undertaken. Further discussions at the next CAMHS Lead Commissioner meeting at the end of November. | 2017-09-01 | Nigel Parkes | R
12.1 | Compliance with NICE Quality Standards | Commissioners to ensure that all providers have a process in place for taking account of NICE guidance in the delivery of services and providing assurance around this. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2015-12-01 | Nigel Parkes | C
12.11 | OFSTED and CQC | No Action
12.12 | Joint CQC/Ofsted Cross Inspectorate View | No Action
LAC2-4 | Ensure that the Virtual School team continue to provide on-going ‘challenge and support’ to schools in order to ensure that children in care make good or better progress during the 2015 / 2016 and 2016 / 2017 academic years |  | Virtual Head now full time, school attends all PEP meetings, permanent exclusions averted, increased % LAC in good or better schools. This work is now business as usual and part of the role of Virtual School | Oct-16 and Oct-17 | Peter Douglas & Tina Hohn | Completed Sept 2016
LAC2-5 | Support schools to ensure all children in care have positive destinations of choice to make a successful education/employment /training transition into post-16 |  | Strong partnerships developed with Leaving Care and Early Help. Roles clearly defined. Traineeships and pre-apprenticeships plus work experience being explored. Currently advertising to fill vacant post-16 LAC advocate post. | 2016-12-01 | Peter Douglas | Closed January 2017
LAC2-6 | Identify and establish best practice for the use of the Pupil Premium and undertake an impact analysis to inform how practice can be developed and improved |  | LAC pupil premium clearly linked to targets in PEP. Some schools still not providing SMART targets. Ongoing training provided to support. | 2017-01-01 | Daniel Chedgzoy | Closed January 2017
LAC2-7 | Establish a system and process to use accurate data regarding attendance and exclusions to support engagement and manage the risks associated with children in care missing school and being out of education |  | Welfare Call has commenced. Action plan currently being developed within Virtual School to use data appropriately. Data to be shared with Early Help and Social Care. | 2017-03-01 | Daniel Chedgzoy | Closed January 2017
LAC2-8 | Develop the Designated Teacher Network and other networking opportunities to develop and share best practice |  | Conference took place in the summer (Attachment conference) as part of the Designated Teacher network agenda. Next DT meeting is 8th November. | 2017-03-01 | Lorraine Dale | Closed January 2017
LAC2-9 | To address the recommendations from the Virtual School Review not included above: allocated budget for VS, address capacity issues at KS4 / Post 16 and administration support, development of post 16 advocacy role to become post 16 coordinator reporting to VH |  | Report no longer required as actions to address recommendations are underway. The budget situation is being addressed through High Needs block. The regrade of the Business support and an apprentice have been approved by DLT (10.10.16). A request for an additional advocate (to be funded by LAC PP) has been submitted for DLT approval (17.10.16). | 2016-12-01 | Lorraine Dale | Closed January 2017
LAC2-10 | Provide support to schools so that they become ‘Attachment Aware’ and are able to improve support for the emotional health and well-being of children in care and improve school placement stability |  | LAC EP has been appointed (job-share secondment from LA service). Will commence on 1st December 2016. This role will lead a large piece of 'attachment' work to support schools (and carers). Day 1 of the Attachment Lead training took place on 30th Sept and was extremely successful. The participating schools must provide a case study of the impact in their schools and deliver a workshop at a DT conference to be scheduled for summer 2017. | 2017-09-01 | Lorraine Dale | Closed January 2017
Outcomes and Differences made:
Evidence Bank |  |  |  |  | Date Received / Ref

## 13. Access & Waiting Times
Access & Waiting Times
Owner: |  | Katie Simpson
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
PERM-1 | Develop and implement a Special Guardianship Policy and Procedure and promote across the Service. |  | The SGO Policy and procedure was approved in June 2016 and has been implemented into practice and understood by the Social Workers and IRO's. | 2016-10-01 | Ian Walker | Complete Nov 16
PERM-2 | Develop process guidance and a flow chart to map the care pathway for children entering care and making their journey to permanence and align this with the statutory reviewing process and relevant other resource decision making panels, where appropriate. Also raised as a finding by Ofsted in the LAC Monitoring Visit Oct 2016 Remedial action required following evidence challenge in January 2017 |  | Planning for permanence has become a key focus and includes the recently formed permanency improvement board. Process guidance and flow chart have been implemented and permanence planning tracker meetings have been re-launched. Any issues in respect of performance will be picked up within the tracker meetings. | 2016-09-01 | Ian Walker | Complete Nov 16
PERM-3 | Co-produce with the Practitioners Forum, and taking the Beyond Auditing feedback into account, a series of thematic practice seminars and deliver this to social workers working with children and young people in care |  | A series of thematic practice seminars have been scheduled and a programme is in place up to the end of December 2016 as part of the broader learning and development work lead by the PSW. | 2016-09-01 | Sarah Hunt/Vicky Schofield | Completed Oct 2016
Access & Waiting Times
13 | DNA policy | 13a RDaSH to undertake periodical audits to understand how the DNA policy is working and to ensure that patients are still not just being discharged from services when they still have a need. | ACTION COMPLETE – Please see Action Plan V12 for detail | Dec-15 then every 6 months | RDaSH | C
|  | 13.1 Ongoing DNA Audits. | 03.06.2016 – Katie Simpson –Audit completed. Findings to be reviewed internally and recommendations to be actioned within an update to the policy. 12.08.2016 Katie Simpson – DNA Audit findings indicate not 100% compliant with the policy in all cases. Recommendations identified to address this; actions to be completed by the end of Sept-16 and a re-audit to be completed Dec-16. Updates to policy in line with Future in Mind required and being worked up. Action plan in place to address this. 19.10.16 Audit complete and recommendations have been circulated for update. KS currently looking at the policy in terms of wording re Future in Mind. 18.11.2016 Katie Simpson – The service is working on the implementation of the audit recommendations. The policy continues to be reviewed, with the review expected to be completed Dec/Jan. 14.12.2016 CAMHS Contract & Performance Meeting - RCCG are looking to review the DNA target as part of the 2017/19 contract. The current target is 10% but CAMHS have been performing below 7% all year. Proposal to reduce target to 7%. 11.01.2017 CAMHS Contract & Performance Meeting - IJ informed members the KPI target has been reduced to 9% with a stretch of 7% through contract and internal reporting mechanisms have been developed for positive hotspots and CAMH’s DNA’s. 05.05.2017 Katie Simpson – re-audit of DNAs to be undertaken shortly, following last year’s audit. The service has workedon implementing the recommnedations of the previous audit and continues to do so. The DNA policy is in the process of being updated across the Trust and will form part of the Service Access and Waiting times policy with a clear protocol for children’s DNAs and follow up engagement. | 2016-06-01 | Katie Simpson | G | 08.02.18 Amber to Green
|  |  | 01.11.2017 DNA policy in process of being replaced, new policy will outline the requirements for following up DNAs in line with the FiM national guidance. Re-audit to be undertaken following implementation of new policy. Reporting on DNAs to be enhanced in line with implementaion of new EPR system. | 2018-06-01 | Katie Simpson | B
13.2 | Following up missed appointments | See 13.1a | Re-audit to be undertaken following implementation of new policy. 08.02.18 Barbara Murray to provide an update. | 2016-06-01 | Katie Simpson | A
Reporting on DNAs to be enhanced in line with implementation of new EPR system.
17.01.18 KS to discuss with Iona Johnson as this has been done but not yet been rolled out.
13.3 | Flexible Appointments | 13.3a Undertake a scoping exercise with patients and their families to understand how flexible appointment times could be offered to encourage attendance and reduce DNA’s. | ACTION COMPLETE – Please see Action Plan V16 for detail | 2016-03-01 | Katie Simpson | C
|  | 13.3b Ensure that flexible appointment times are offered to Children, Young People and their families to enable them to attend services. | 18.11.2016 Katie Simpson – Patient Survey completed during July. The survey has highlighted that service users would be interested in appointments being offered between 4pm and 6pm and almost 50% of respondents would be interested in weekend appointments. The most popular locations for appointments are at GP surgeries or in schools. The service is reviewing the feedback and will be implementing revised service times and locations in response. Some of this will be piloted as part of the waiting times initiative, with the offer of evening and Saturday clinics. 11.01.2017 CAMHS Contract & Performance Meeting - GP confirmed additional appointments are now being offered on Saturday’s and Tues/Thurs evenings to improve access to the service. ADHD parenting courses have also been set up. 05.05.2017 – service is reviewing service delivery times in line with feedback received from clients. Some extended hours have been trialled as part of the waiting times initiatives. 01.11.2017 Work continues with the service to offer a more flexible approach to service delivery appointment times. 17.01.18 BM felt this is not an issue as they are flexible. There may be a need to be demonstrate. JP suggested a short survey amongst services. BM to action. | 2016-09-01 | Katie Simpson | G | 08.02.18 Amber to Green
|  |  | 08.02.18 Review with Parents - ESQ Data re-appointments | 2018-09-01 |  | B | 08.02.18 Added
|  |  |  | 2019-09-01 |  | B | 08.02.18 Added
13.4 | CAMHS Minimum Dataset | RDaSH to continue to work towards implementation of the combined Mental Health Minimum Data Set from April 2016. This includes the CAMHS MDS. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-03-01 | Katie Simpson | C
13.5 | CAMHS Outcome Reporting | 13.5a RDaSH to continue to develop CAMHS outcomes reporting through the 2015/16 CQUIN. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-03-01 | Katie Simpson | C
|  | 13.5b Review CAMHS outcome reporting through 2016/17 CQUIN | 05.05.2017 Katie Simpson - 16/17 CQUIN was transition? Work is being undertaken with the systems team to develop the outcomes reporting and this is expected in the summer. Alongisde this work has started with the implementation team for S1 so that when the service transfers to the new system this information can be captured. Without robust reporting it is unclear what development work is required with the team to improve this. 01.11.2017 Should this be re-worded or closed as this CQUIN is now complete? Work is underway as part of the new EPR system implementation on robust routine outcome data capture and reporting. New EPR system will go live 30th November. In addition the service will identify ROM champions and refreshed training will be delivered to practitioners. | 2017-03-01 | Katie Simpson | C
|  | 13.5c RDaSH continue to develop Outcome reporting |  | 2018-03-01 | Katie Simpson | B
13.6 | Work with non-NHS providers to ensure flow data for key national metrics in MHDS |  | 05.05.2017 Nigel Parkes – Work still to start. 06.06.2017 Nigel Parkes to provide an update 11.10.17 Nigel Parkes - Work ongoing 01.11.17 Identified to NHS England potential providers who maybe approptiate to submit data to the MHSDS 08.02.17. Barbarba Murray to attend meetings re MHSDS |  |  | A
13.7 | Early Intervention in Psychosis Waiting Time Standards | 13.7 RDaSH to ensure that they are able to meet the new access and waiting time standard, which requires that, by 1 April 2016, more than 50% of people experiencing a first episode of psychosis will be treated with a NICE approved care package within two weeks of referral. This to be in line with the published guidance and will meet both elements of the standard, i.e. the wait from referral to treatment and whether the treatment accessed is NICE concordant. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-03-01 | Katie Simpson | C
13.8 | Nice Concordant Treatment and Measurement of Outcomes | See above action 13.6
13.9 | Performance Framework for Emontional Wellbeing & Mental Health Services In Rotherham | 13.9a Stakeholders to scope out performance information currently available. | 09.06.16 Nigel Parkes – No progress with this action as yet. 17.11.16 Paul Theaker - Currently adapting national performance template as a framework for local use. 04.05.2017 Paul Theaker - Performance framework drafted, to be shared with stakeholders | 2016-12-01 | Rebecca Mcalister | C
|  | 13.9b Stakeholders to work together to develop a common performance framework. | 09.06.16 Nigel Parkes – As above. Links to comment above 30.10.17 Action now completed | 2017-03-01 | Rebecca Mcalister | C
|  | 13.9c Stakeholders to implement a common performance framework. | 30.10.17 Action now completed 08.02.18 Action is picked up under the AS&J work | 2017-09-01 | Rebecca Mcalister | C
13.1 | RDaSH CAMHS Discharge Process | 13.10a Develop and undertake an audit to include the following themes :- • The practice and quality of discharge planning • Patient and family feedback on the quality of discharge and transition to other services • The role of the peer support worker in supporting the discharge process. • The number of patients that are re-referred to the service following discharge. • The number of patients that are re- referred and accepted into the service following sign-posting to other agencies or 'rejected' at the point of referral | 29.02.16 Claire Strachan : we need to identify a lead for this action 10.03.16 Barbara Murray- cases are reviewed with clinicians to ensure that discharge processes are undertaken effectively. Audit work is required with an identified lead for this to be highlighted in the next month. Root cause analysis is undertaken when a young person is re-referred to service within a month of discharge. 06.05.2016 Katie Simpson – BM advised audit lead to be identified. 03.06.2016 Katie Simpson – audit programme in development. 18.11.2016 Katie Simpson – audit has been delayed due to implementation of new service model and focus on improving assessment and treatment waits. Would like to consider a revised timescale for completion. 14.12.2016 CAMHS Contract & Performance Meeting - KS to confirm audit completion date. 11.01.2017 CAMHS Contract & Performance Meeting - NP had discussed this with Barbara Murray and work is ongoing. 05.05.2017 Katie Simpson – Work is ongoing and nearing completion 01.11.2017 Work is underway on this audit, however it has been delayed. Expected end of Dec 2017 17.01.2018 BM to undertake. JP requested completion by the end of March. | 2016-03-01 | RDaSH | A
|  | 13.10b Repeat the audit from 36.4a every year going forward. | 05.05.2017 – first audit still in progress, this will be completed again 2018 | Mar-17 & yearly | Katie Simpson | A
13.11 | Forward view of Rotherham CAMHS Services to 2020 | 13.11 | 05.05.2017 Nigel Parkes – Work not commenced yet. NP to organise meeting with parties to discuss. 11.10.17 Nigel Parkes - On going 01.11.17 The CCG has outlined future financial spend relating to the CAMHS LTP, but further work around workforce and activity needs to commence. | 2017-03-01 | Nigel Parkes | A
Impact, Outcome / Difference made
Evidence Bank |  |  |  |  | Date Received / Ref

## 14. Invest In Serv
Investment in Services
Owner: |  | Nigel Parkes
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
Investment in Services
14 | Children's Mental Health Spend Including Inpatient | 14a Stakeholders working together on the implementation of payment systems for CAMHS | 07.03.16 Nigel Parkes – No further progress re National Payment System for CAMHS 07.12.2016 Nigel Parkes – No further update. 05.05.2017 Nigel Parkes – No further update 01.11.17 No Further National Guidance | 2016-09-01 | Nigel Parkes | A
|  | 14b Stakeholders to work together on any initiatives regarding Personal Health Budgets. | 07.12.2016 Nigel Parkes- This work has not started yet. 05.05.2017 Nigel Parkes – RCCG is developing this area 11.10.17 Nigel Parkes - on going | 2017-03-01 | Nigel Parkes | A
14.1 | NHS England will be able to identify the overall children's mental health spend by NHS | The CAMHS Transformation Plan will identify investment by commissioners in Children & Young people’s mental health services. | Action Complete - Please see Action Plan V10 | 2015-10-01 | Nigel Parkes | C
14.2 | Child and Adolescent Mental Health Funding Flows Across Education, Health, Social Care | RCCG to co-ordinate further work to understand child & adolescent mental health funding flows. This will particularly focus on funding by schools & colleges. | 05.05.2017 Nigel Parkes – NP to set up meeting to start discussions. 01.11.17 RMBC proposing to start a piece of work around this 06.06.17 – Nigel Parkes working on 11.10.17 Nigel Parkes to update 13.02.18 Nigel Parkes - This is picked up through the CAMHS LTP quarterly reports. | 2017-03-01 | Nigel Parkes | A
06.06.17 – Nigel Parkes working on
.
Impact, Outcome / Difference made:
Evidence Bank |  |  |  |  | Date Received / Ref

## 15. Workforce
Workforce
Owner: |  | Rebecca McAlister
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
Workforce
15.1 | Implementing the Recommendations of the Carter Review of Initial Teacher Training (ITT) | Nationally driven Also, not just initial training needs to be a rolling programme to deepen awareness.
15.2 | Investment in Commissioning Capability and Development | Commissioners from RCCG, RMBC and NHS England to assess attendance at national mental health commissioning capability development programme courses. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-03-01 | Nigel Parkes | G
15.3 | Training for Staff Working in commissioning of Children and Young People's services | 100% of staff projected to received CYIAPT training do so. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-03-01 | Katie Simpson | G
15.4 | CYIAPT Training | 15.4a RDaSH and MIND to ensure that they continue to be part of the CYPIAPT initiative and to roll out training as appropriate. | 22.12.15 – RDaSH staff are participating in training courses over 2015/16. 15.02.15 Frankie Hibbard - MIND staff are participating in training course over the next year. 10.03.16 Barbara Murray- there are potentially further opportunities for partners to engage in the CYP-IAPT training from September 2016 (counselling, under 5’s), awaiting national confirmation of the expectations of education/ voluntary sector organisations in relation to reporting etc. 07.12.2016 Nigel Parkes – RCCG has committed to supporting 2 new psychological wellbeing practitioners (PWP’s) from 2018/19 05.05.2017 Katie Simpson – PWPs in post from Mid-April. The team are scoping their training requirements for the next CYPIAPT wave. The service continues to actively engage in the CYIAPT partnership and associated developments. 01.11.2017 A number of RDaSH staff will be undertaking CYPIAPT training over the next year. 1 x CBT 1 x SFP Self-harm 2 x Leadership | Ongoing | Katie Simpson | G
|  |  | RDaSH Continues to be part of the CYPIAPT Initiative. | 2018-09-01 | Katie Simpson | B
|  | 15.4b RDaSH provides regular updates of its performance against the requirements of ‘Delivering with, delivering well’ | 01.11.2017 Quarterly IAPT submission shared | Ongoing | Katie Simpson | A
|  | 15.4c All staff should be trained to practice in a non-discriminatory way with respect to gender, ethnicity, religion and disability. | See 15.6 below.
|  | 15.4d Skills gaps in the current workforce around the full range of evidence-based therapies recommended by NICE shall be addressed. | See 15.6 below.
|  | 15.4e Skills gaps in the training of staff working with children and young people with Learning Difficulties, Autistic Spectrum Disorder, and those in inpatient settings shall be addressed. | See 15.6 below. Also 8.1b, 8.1c and 8.1d above.
|  | 15.4f Counsellors working in schools and the community will receive further training toimprove evidence-based care. | See 15.6 below. Also 8.2a above.
15.5 | CYP IAPT Transformation Programme | National actions.
15.6 | Workforce Strategy | 15.6a A workforce development strategy will be formulated to identify needs for the wider CAMHS workforce in Rotherham. This is supported by extra funding in 2015/16 21.04.16 Nigel Parkes – This relates to local priority scheme 6 in the LTP. |  | 2016-03-01 | Ruth Fletcher-Brown | A
|  | 15.6b Work with the local Workforce Action Board to clarify future workforce arrangements | RMBC update required 06.06.17 Ruth Fletcher-Brown to provide an updated 11.10.17 Ruth Fletecher- Brown - Need for re-word and no longer relevant to Ruth and Rebecca Mcalister | 2016-12-01 | Rebecca Mcalister | A
|  | 15.6c Evaluation of the Workforce Development Strategy | RMBC update required 06.06.17 Ruth Fletcher-Brown to provide an updated 11.10.17 Ruth Fletecher- Brown - Need for re-word and no longer relevant to Ruth and Rebecca Mcalister | 2017-03-01 | Rebecca Mcalister | A
|  | 15.6d A screening tool will be developed to identify children who may be experiencing poor mental health. This is supported by extra funding in 2015/16 | 26.01.16 Sarah McCall & Ruth Fletcher-Brown - Meeting being scheduled with RDaSH to progress. 01.03.16 Sarah McCall - Meeting with Barbara Murray pending to progress this. 07.04.2016 Ruth Fletcher-Brown - meeting pending to take this forwards 31.03.16 RFB – work ongoing with RDASH to develop. 11.08.2016 Ruth Fletcher-Brown - Screening tool to be piloted. 17.11.16 Paul Theaker & Ruth Fletcher Brown - to follow refreshed pathways 04.05.2017 Ruth Fletcher-Brown - See earlier relating to screening tool | 2016-03-01 | Rebecca Mcalister | A
|  | 15.6e Evaluation of the Screening Tool. | RMBC update required 06.06.17 RMB to provide an update 11.10.17 Ruth Fletecher- Brown - Need for re-word and no longer relevant to Ruth and Rebecca Mcalister | 2016-09-01 | Rebecca Mcalister | A
|  | 15.6f Actively promote the ‘MindEd’ website (www.minded.org.uk) as a source of good quality online evidence based training suitable for different professionals and work with providers to ensure that staff are allowed time to complete the training. | ACTIONS COMPLETE – Please see Action Plan V10 for detail | 2016-03-01 | Ruth Fletcher-Brown | C
|  | 15.6g Develop joint agency workforce plan with key organisations, including schools and colleges detailing how capacity and capability will be increased (links to CYP IAPT). | 19.01.17 Nigel Parkes – NP,PT,RFB,AL met to discuss workforce planning - Y&H producing a framework for education by Feb/March 2017. Will meet again end of February. 05.05.2017 Nigel Parkes – Awaiting results of Y&H framework 01.11.17 The Y&H Framework for education is being piloted at Wales High School | 2016-12-01 | Nigel Parkes | A
|  | 15.6h Further develop the workforce plan to show how the workforce will be developed up to 2020. This will include the provision of both statutory and non-statutory services including Schools based. | 01.11.17 This work still needs to be developed | 2017-06-01 | Nigel Parkes | R
15.7 | Professionals trained to be able to recognise the value & impact of mental health in children and young people | See 15.6a above.
15.8 | Professionals trained to promote good mental health to children and young people | See 15.6a above.
15.9 | Professionals trained to identify mental health problems early in children and young people | See 15.6a above with particular emphasis on schools/colleges and to include all staff involved in the classroom.
15.1 | Professionals trained to offer appropriate support to children and young people with mental health problems. | See 15.6a above with particular emphasis on schools/colleges and to include all staff involved in the classroom.
15.11 | Professionals trained to refer appropriately to more targeted and specialist support. | See 15.6a above, but also links to action 7.1a relating to RDaSH CAMHS SPA and action 8.2 relating to the CAMHS 'Top Tips' and 'Directory of Services'.
15.12 | Professionals trained to use feedback gathered meaningfully on a regular basis to guide treatment | See 15.6a above.
15.13 | Professionals trained to work in digital environment with young people who are using online channels | See 15.6a above.
Impact, Outcome / Difference made:
Evidence Bank |  |  |  |  | Date Received / Ref

## 16. Eating Dis
Eating Disorders
Owner: |  | Katie Simpson
Key actions to address key judgements: |  |  | Progress | By When | Action Owner | BRAG
Eating Disorders
16 | Eating Disorders | 16a Establish a Task and Finish Group to work with Partners from Doncaster CCG, North Lincolnshire CCG and RDaSH to develop an enhanced community eating disorder service | Action Comptete please see Action Plan V10 | 2015-12-01 | Nigel Parkes | C
|  | 16b Agree a Community Eating Disorder Service Specification to be used by all 3 CCGs | Action Comptete please see Action Plan V10 | 2016-02-01 | Nigel Parkes | C
Nigel Parkes
|  | 16c New service model to have commenced | Action Comptete please see Action Plan V12 | 2016-02-01 | Nigel Parkes | C
|  | 16d External evaluation of the new service to be commissioned by Doncaster CCG on behalf of the 3 CCGs | Action Completed please see Action Plan V10 | 2016-03-01 | Nigel Parkes | C
|  | 16e Community Eating Disorder Service Specification and EIA to be include in the RDaSH /Standard Contract | Action Completed please see Action Plan V12 | 2016-05-01 | Nigel Parkes | C
|  | 16f Community Eating Disorder Service Implementation plan to be agreed by CCGs & RDaSH | Action Completed please see Action Plan V15 | 2016-05-01 | Nigel Parkes | C
|  | 16g Delivery of the Community Eating Disorder Service Implementation plan. | This plan will be monitored at both local and footprint level Nigel Parkes - Nov 2017 - Evaluation Report received and being assessed. 13.02.18 - The evaluation report was not robust. Monitoring of the service will continue through monthly reporting. | 2017-04-01 | Nigel Parkes | A
Impact, Outcome / Difference made
Evidence Bank |  |  |  |  | Date Received / Ref