## PC Workstream Monitoring
Objective | Key lead/s | Individual/s | Workstream and current RAG rating | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | Comments
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Quality driven services | Rachel Garrison | Julie Murphy | Rolling process of Contract & Quality Visits | [20 empty] | Effective rolling programme in place, and practices are prioritised as necesssary
|  | Rachel Garrison / Sara Hartley | Subject specific Peer Review visits | bar: 2015/16 Q1 to 2016/17 Q4; 2017/18 Q4 to 2019/20 Q4
|  | Rachel Garrison | CQC reviews - action plans, peer reviews, support following visits | [20 empty] | Only one practice remains in 'requires improvement'
|  | Julie Dale | Overall practice performance monitoring via the Dashboard | [20 empty] | As perthe Primary Care Dasboard | bar: 2015/16 Q1 to 2015/16 Q4; 2017/18 Q1 to 2019/20 Q4
|  | Rachel Garrison | Continue PLT support | bar: 2015/16 Q1 to 2015/16 Q4; 2017/18 Q1 to 2019/20 Q4
|  | Rachel Garrison | Ongoing liaison with the Quality & Safeguarding Teams | bar: 2015/16 Q1 to 2015/16 Q4; 2017/18 Q1 to 2019/20 Q4
|  | Rachel Garrison | Implementation , monitoring and revision of the Quality Contract | [20 empty] | Progressing well with good practice engagement | bar: 2016/17 Q1 to 2018/19 Q1; 2018/19 Q4 to 2019/20 Q1; 2019/20 Q4
|  | Jo Martin | Optometry secondary to primary transfer | bar: 2017/18 Q1 to 2019/20 Q4
|  | Sara Hartley | Practice resilience in conjunction with NHS England | bar: 2016/17 Q1 to 2016/17 Q2; 2017/18 Q1 to 2017/18 Q2; 2018/19 Q1 to 2018/19 Q2; 2019/20 Q1 to 2019/20 Q2
Services as local as possible | Rachel Garrison | Sara Hartley | Introduction of new Local Enhanced Services, as appropriate
|  | Sara Hartley | Continued movement from secondary to primary care; Denosumab, Testosterone, Ibandronic Acid, Transgender
|  | Julie Dale | Diabetes care; increased primary care involvement | bar: 2016/17 Q1 to 2016/17 Q4; 2017/18 Q3 to 2019/20 Q1
Contracting | Sara Hartley | Julie Murphy / Julie Dale | All contracting of LESs for General Practice, Pharmacy and Optometry | bar: 2015/16 Q3 to 2015/16 Q4; 2016/17 Q3 to 2016/17 Q4; 2017/18 Q3 to 2017/18 Q4; 2018/19 Q3 to 2018/19 Q4; 2019/20 Q3 to 2019/20 Q4
|  | Julie Murphy / Julie Dale | Review and update of LES service specifications | bar: 2015/16 Q3 to 2015/16 Q4; 2016/17 Q3 to 2016/17 Q4; 2017/18 Q3 to 2017/18 Q4; 2018/19 Q3 to 2018/19 Q4; 2019/20 Q3 to 2019/20 Q4
|  | Julie Murphy / Julie Dale | Contract Variations
Equality of service provision | Rachel Garrison | Rachel Garrison | Basket review and implementation | [20 empty] | Dementia under review
|  | Julie Dale | Care home alignment | [20 empty] | Evaluation underway | bar: 2015/16 Q1 to 2015/16 Q4; 2017/18 Q1 to 2019/20 Q4
Increasing appropriate capacity & capability | Avanthi Gunasekera, Jacqui Tuffnell & Rachel Garrison | Rachel Garrison | Workforce diversification; including categories below: | [20 empty] | Practices continually encouraged but slow to respond in some areas. APEX will hopefully demonstrate where efficiencies and savings can be made at practice level, and role reimbursement within PCNs will encourage participation
|  | Julie Murphy | Clinical Pharmacists | bar: 2015/16 Q1 to 2015/16 Q4; 2017/18 Q4 to 2019/20 Q4
|  | Sara Hartley | Associate Physicians; encouraging practices to provide training places
|  | Federation | Student nurses; encouraging practices to provide training places
|  | Federation | Newly qualified nurses; encouraging practices to provide posts
|  | Federation | Encouraging practices to consider recruiting Paramedics
|  | Rachel Garrison / Sara Hartley | Increased use of technology i.e. APEX Insight | [20 empty] | APEX on-hold nationally
|  | Rachel Garrison / Sara Hartley | Supporting practice sustainability
|  | Rachel Garrison | GP Retention Scheme | [20 empty] | Decision made at PCC in January 2019 | bar: 2015/16 Q1 to 2016/17 Q4; 2018/19 Q2 to 2019/20 Q4
|  | Rachel Garrison | International GP Recruitment Programme | [20 empty] | Pace is dictated by the NHSE regional team not RCCG, but we are working to bring interested applicants to Rotherham | bar: 2015/16 Q1 to 2016/17 Q4; 2017/18 Q4 to 2019/20 Q4
Primary care access arrangements | Avanthi Gunasekera & Jo Martin | Federation | Supporting Practice Manager development | bar: 2016/17 Q1 to 2019/20 Q4
|  | Jo Martin | Monitoring of weekend /extended access arrangements | [20 empty] | In place and delivering as per national requirements
New models of care | Avanthi Gunasekera, Jacqui Tuffnell & Jo Martin | Jo Martin | NHS 111 bookings | [20 empty] | National requirement as part of the PCN DES
|  | Jo Martin | Practice collaboration
|  | Jo Martin | CIC development | bar: 2016/17 Q1 to 2019/20 Q4
|  | Jacqui Tuffnell / Jo Martin | Community transformation programme | bar: 2016/17 Q1 to 2016/17 Q4; 2017/18 Q4 to 2019/20 Q4
Self-care | Avanthi Gunasekera, Jo Martin & Rachel Garrison | Sara Hartley | Project plan for full implementation of anticoagulation, Diabetes, BP COPD, self-management | [20 empty] | Plan currently under development | bar: 2015/16 Q1 to 2016/17 Q4; 2017/18 Q4 to 2019/20 Q4
|  | Sara Hartley | Roll-out of Telehealth | [20 empty] | As above | bar: 2016/17 Q1 to 2019/20 Q4
|  | Julie Murphy | Care Navigation | [20 empty] | Good practice engagement, working with community pharmacists to improve response to signposts | bar: 2017/18 Q3 to 2019/20 Q4
|  | Federation | Whzan - Care Home Pilot | [20 empty] | Project behind schedule but progressing | bar: 2017/18 Q4 to 2019/20 Q1
|  | Jo Martin | Use of online services - incorporating access arrangements | [20 empty] | Will be incorporated in the Rotherham App | bar: 2016/17 Q1 to 2016/17 Q4; 2018/19 Q1 to 2019/20 Q1
|  | Jo Martin | E-consultations | [20 empty] | Will be incorporated in the Rotherham App | bar: 2016/17 Q1 to 2016/17 Q4; 2017/18 Q4 to 2019/20 Q1
Robust quality and performance management | Rachel Garrison & Julie Murphy | Rachel Garrison | Procedure in place for managing commissioning / quality issues | bar: 2015/16 Q1 to 2015/16 Q4; 2017/18 Q1 to 2019/20 Q4
|  | Rachel Garrison | Performance management arrangements being reviewed as part of the quality contract work | bar: 2016/17 Q1 to 2016/17 Q4; 2017/18 Q4 to 2019/20 Q4
Continued improvements - Medicines Management | Stuart Lakin | Rachel Garrison | Waste campaign | bar: 2015/16 Q1 to 2016/17 Q4; 2017/18 Q4 to 2019/20 Q1
|  | Rachel Garrison | Supporting practices with clinical Pharmacist development | bar: 2016/17 Q1 to 2019/20 Q4
Engaging patient-optimised pathways | Helen Wyatt |  | PPG development | bar: 2015/16 Q1 to 2015/16 Q4; 2017/18 Q4 to 2019/20 Q1
|  |  | Co-production of pathways | [20 empty] | PPE needs to be involved in pathway development in the initial stages for this to be delivered | bar: 2015/16 Q1 to 2019/20 Q1
Carers support | bar: 2015/16 Q1 to 2019/20 Q1
Estates | Jacqui Tuffnell, Jo Martin NHS England & NHS Property Services | Primary Care Team | Waverley (January 2017 to January 2018) | [20 empty] | Plan in place to allow for recruitment of patients on site, pending the health centre build | bar: 2016/17 Q4 to 2019/20 Q2
|  | Rachel Garrison | Mapping of Primary Care Estate and 5 year plan | [20 empty] | Underway as per the RCCG Strategy, working on bids to support feasibility studies | bar: 2015/16 Q1 to 2015/16 Q4; 2017/18 Q1 to 2019/20 Q1
|  | Sara Hartley | Management of required actions from practice surveys | [20 empty] | Linked to delays in Capital and BAU bids | bar: 2016/17 Q1 to 2016/17 Q2; 2017/18 Q1 to 2019/20 Q1
|  | Sara Hartley | Capital Bids - ETTF and BAU | bar: 2016/17 Q3 to 2019/20 Q1
IT | Andy Clayton & Wendy Lawrence | Jo Martin | Remote consultation implementation | bar: 2017/18 Q1 to 2019/20 Q1
Implementation of the Rotherham App | bar: 2017/18 Q1 to 2019/20 Q1
NHS England | Paul Barringer | Rachel Garrison | Collaborating with community pharmacies via the Local Pharmacy Committee
Investment & Evolution | Rachel Garrison | Primary Care Team | Delivering the actions of the NHS Long Term Plan for Primary Care | [20 empty] | Details provided on another tab | bar: 2019/20 Q1 to 2019/20 Q4
Completed workstreams:
Productive General Practice Programme
Supporting the CIC to bid for 2nd round funding for clinical Pharmacists
Review of case management arrangements to incorporate care home patients
Medical Documentation Training
Procurement of Waverley provider
Approve Waverley build
Approve Canklow move
Canklow move (actual)
GP main practice surveys
All GPs have a laptop to enable remote working
Procurement of the Rotherham App
All practices have Wi-Fi enabled
Optometry support to practices - direct cataract referral
Local digital roadmap submitted
Use of EPaCCs
Web Optimisation
Increasing the use of E-Referral
Performance dashboard development rollout
Review of Doncaster dashboard
CIC Federation structure
New full access arrangements in place by October 2018
EPS implementation

## Investment & Evolution
Category | Who's Responsible | Reference | Deadline | CCG Lead | Relevance to CCG workplan | Comments by exception
PCNs | National | NHS England and GPC England issue Network Agreement and 2019/20 Contract DES | 2019-03-29 | Rachel Garrison | For PCN establishment
Digital | Primary Care | Requirement for Electronic ordering of repeat prescriptions and using electronic repeat dispensing for all patients for whom it is clinically appropriate as a default | 2019-03-31 | Stuart Lakin | To note and action as appropriate
QOF | National | 28 Indicators retired | 2019-03-31 | Avanthi Gunasekera | Link to Quality Contract
Digital | National | GP IT Operating Model update scheduled | 2019-03-31 | Andy Clayton | To note and action as appropriate
Indemnity | National | State negligence scheme | 2019-04-01 | Not applicable
PCNs | National | Practices able to claim a Network Participation Practice Payment - agreement template available | 2019-04-01 | Rachel Garrison | For PCN establishment
Sustainable & Resilient | National | Clinical Negligence Scheme for General Practice starts | 2019-04-01 | Not applicable
QOF | National | 15 new indicators introduced | 2019-04-01 | Avanthi Gunasekera | Link to Quality Contract
QOF | National | QOF Quality Improvement domain introduced - end of life care and prescribing safety | 2019-04-01 | Avanthi Gunasekera | Link to Quality Contract
Contractual Changes | Contract | Contraception services will no longer be an Additional Service under the Regulations but will become part of Essential Services | 2019-04-01 | Not applicable
Contractual Changes | Contract | Practices will be able to claim a Network Participation Practice | 2019-04-01 | Rachel Garrison | For PCN establishment
Contractual Changes | Contract | Ban on private GP services | 2019-04-01 | Not applicable
Contractual Changes | Contract | Prescribers need to write SH as an endorsement on the FP10 form for medication to treat STIs | 2019-04-01 | Not applicable
Contractual Changes | Contract | Practices will be required to provide data in support of contract requirements, including Network DES data | 2019-04-01 | Sara Hartley | To collate returns
Contractual Changes | Contract | New patient registrants will have full online access to prospective data from April 2019 | 2019-04-01 | Sara Hartley | To collate returns
Contractual Changes | Contract | Rurality index payment will be amended to apply to patients living within a practice catchment area only, rather than all patients | 2019-04-01 | Not applicable
Contractual Changes | Contract | London adjustment will be amended to apply to patients' resident in London, rather than registered in a London-based practice. | 2019-04-01 | Not applicable
Contractual Changes | Contract | Practices will allow the direct booking of clinician-assessed patient appointments from 111 into practice | 2019-04-01 | Joanne Martin | Link to App
Contractual Changes | Contract | Practices will make available 1 appointment per 3000 patients per day from direct booking from 111 | 2019-04-01 | Joanne Martin | Link to App
Contractual Changes | Contract | The existing Duty of Co-operation requirements will be amended to facilitate data sharing between providers to support integrated provision of services | 2019-04-01 | Not applicable
Contractual Changes | Contract | Practices will be required to support six national NHS marketing campaigns by having displays on premises | 2019-04-01 | Sara Hartley | To collate returns
Contractual Changes | Contract | NHS England will reimburse the cost of locum cover for GPs taking shared parental leave in the same way that is done for those taking maternity leave | 2019-04-01 | Not applicable
Contractual Changes | Contract | GPs with total NHS earnings above £150,000 per annum will be listed by name and earnings in a national publication | 2019-04-01 | Not applicable
Contractual Changes | Contract | Childhood seasonal influenza uplifted to £10.06 | 2019-04-01 | Not applicable
Contractual Changes | Contract | Pertussis uplifted to £10.06 | 2019-04-01 | Not applicable
Contractual Changes | Contract | Seasonal influenza and pneumococcal polysaccharide uplifted to £10.06 | 2019-04-01 | Not applicable
Contractual Changes | Contract | Care home and social care staff will be added to the categories of people entitles to a flu vaccine at an IOS fee of £10.06 | 2019-04-01 | Not applicable
Contractual Changes | Contract | The Influenza and Pneumococcal Immunisation Scheme DES specification will be revised to explicitly underline that in order for practices to receive payment for the vaccination and reimbursement for the vaccine, they need to use the flu vaccine recommended in NHSE guidance. | 2019-04-01 | Not applicable
Contractual Changes | Contract | Any HPV vaccination of women aged 18-25 will be paid at IOS rate of £10.06 | 2019-04-01 | Not applicable
Contractual Changes | Contract | Item of service payment of £5 per patient for the extra cost of a catch-up campaign for the Measles, Mumps and Rubella (MMR) vaccine for 10 and 11-year olds in the light of the current measles outbreaks. Payment will be made for each child recorded as unvaccinated. | 2019-04-01 | Not applicable
Sustainable & Resilient | National | Programme Extension - International Recruitment (5 Years) | 2019-04-01 | Rachel Garrison | To note and action as appropriate
Sustainable & Resilient | National | Programme Extension - Retained Doctors (5 Years) | 2019-04-01 | Rachel Garrison | To note and action as appropriate
Sustainable & Resilient | National | Programme Extension - GP Retention (5 Years) | 2019-04-01 | Rachel Garrison | To note and action as appropriate
Sustainable & Resilient | National | Programme Extension - Practice Resilience (5 Years) | 2019-04-01 | Sara Hartley | To note and action as appropriate
Sustainable & Resilient | National | Programme Extension - Mental Health services for GPs (5 Years) | 2019-04-01 | Sara Hartley | To note and action as appropriate
Sustainable & Resilient | National | Programme Extension - Time for Care National Development Programme (5 Years) | 2019-04-01 | Rachel Garrison | To note and action as appropriate
Workforce | National | Additional Roles Reimbursement Scheme extended to include Clinical Pharmacists | 2019-04-01 | Rachel Garrison | For PCN establishment
Workforce | National | Additional Roles Reimbursement Scheme extended to include Social Prescribers | 2019-04-01 | Rachel Garrison | For PCN establishment
Extended Access | National | NHS England review starts assessing integration between 111, UTCs and GP | 2019-04-01 | Not applicable
PCNs | Networks | All PCNs submit DES registration information to CCGs | 2019-05-15 | Rachel Garrison | To collate returns
PCNs | CCGs | CCGs must confirm the Network DES registration requirements have been met | 2019-05-31 | Rachel Garrison | To collate returns
PCNs | CCGs | CCGs confirm network coverage and approve variation to GMS, PMS and APMS contracts | 2019-05-31 | Rachel Garrison | To collate returns
PCNs | CCGs | The establishment of PCNs within the region to ensure that every practice is a part of a local PCN (30,000-50,000 patients) | 2019-06-30 | Rachel Garrison | To collate returns
PCNs | CCGs | Each network must have a Clinical Director and a Network Agreement in place | 2019-06-30 | Rachel Garrison | To collate returns
PCNs | CCGs | 100% Coverage of Network Contract DES - DES goes live | 2019-06-30 | Rachel Garrison | To collate returns
PCNs | National/CCGs | Ensure that PCNs are provided with primary care data analytics for population segmentation and risk stratification based on national data, complemented with local flows, to allow them to understand healthcare needs for symptomatic and prevention programmes including screening and immunisation services | 2019-06-30 | Joanne Martin / Rachel Garrison | To deliver local agenda
PCNs | CCGs | PCN Development local plan published | 2019-06-30 | Joanne Martin | To note and action as appropriate
Digital | Practices | All practices will ensure at least 25% of appointments are available for online booking | 2019-06-30 | Joanne Martin | Link to App
PCNs | Primary Care | NHS England to resolve any Network DES registration issues with CCGs | 2019-06-30 | Rachel Garrison | To note and action as appropriate
Extended Access | CCGs | Extended Hours Access DES requirements introduced across all practices in every network | 2019-06-30 | Sara Hartley | To ensure compliance
PCNs | CCGs | Provide a minimum of £1.50 per head of financial support to PCNs for their management and organisational development. 01/07/2019 - 31/03/2024 | 2019-07-01 | Rachel Garrison | To note and action as appropriate
Workforce | National | Network staff reimbursement funding is made available - clinical pharmacist and social prescribing link worker | 2019-07-01 | Rachel Garrison | To note and action as appropriate
Contractual Changes | Contract | All practices will ensure at least 25% of appointments are available for online booking | 2019-07-01 | Joanne Martin | Link to App
Digital | National | NHS App available to 100% of the population | 2019-07-31 | Not applicable
Digital | Practices | Practices must register a practice email address with MHRA CAS alert system and act on CAS alerts | 2019-09-30 | Not applicable
Digital | Practices | Practices must register an emergency mobile phone number to MHRA CAS | 2019-09-30 | Not applicable
Contractual Changes | Contract | Practices must have completed all MHRA CAS registration and notification information | 2019-10-01 | Not applicable
Contractual Changes | Contract | When using the NHS logo, practices will be required to adhere to NHS identity guidelines | 2019-10-01 | Not applicable
Sustainable & Resilient | Primary Care | 75% of 19/20 sustainability and resilience funding to be spent | 2019-12-31 | Sara Hartley | To note and action as appropriate
Digital | National | GP IT Futures replace GP Systems of Choice | 2019-12-31 | Andy Clayton | To note and action as appropriate
PCNs | National | Support PCNs in their development and ensure they are practically supported to access the PCN Development Programme. | 2020-03-31 | Joanne Martin | To facililitate development
PCNs | CCGs | Activity of PCN Development local plan completed | 2020-03-31 | Joanne Martin | To facililitate development
Sustainable & Resilient | Primary Care | 100% of 19/20 sustainability and resilience funding to be spent | 2020-03-31 | Sara Hartley | To note and action as appropriate
Workforce | Primary Care | Development of a detailed STP/ICS workforce plan with trajectories | 2020-03-31 | Rachel Garrison | Link to RCCG workforce plan
Workforce | National | Ensure all staff in primary care settings have access to the support of a training hub and capacity to participate in training programmes (e.g. e-learning resources held by HEE); and that there is a plan to develop the agreed set of required functions. | 2020-03-31 | Not applicable
Workforce | National | Continue with commissioning and deployment of 180 pharmacists and 60 pharmacy technician posts (funded by the Pharmacy Integration Fund, with support from NHS England Regional Independent Care Sector Programme Management Offices), to improve medicines optimisation for care home residents. | 2020-03-31 | Stuart Lakin | To note and action as appropriate
QOF | National | Review of heart failure, asthma and chronic obstructive pulmonary disease QOF domains | 2020-03-31 | Avanthi Gunasekera | Link to Quality Contract
Digital | Practices | All practices will be giving patients access online to correspondence and records | 2020-04-01 | Joanne Martin | Link to App
Digital | Practices | Practices must offer online consultations | 2020-04-01 | Joanne Martin | Link to App
Digital | Practices | All practices will need an updated an informative online presence, with key information being available as metadata | 2020-04-01 | Andy Clayton | To note and action as appropriate
Digital | Practices | Practices will no longer use facsimile machines | 2020-04-01 | Andy Clayton | To note and action as appropriate
PCNs | National | National Network Services start under the 2020/21 Network Contract DES | 2020-04-01 | Sara Hartley | To ensure compliance
Workforce | National | Each network will be allotted a single combined maximum reimbursement sum, covering all five staff roles - followed by 2020 physician associates and 2021 first contact community paramedics | 2020-04-01 | Rachel Garrison | To note and action as appropriate
QOF | National | Further changes introduced - post review of heart failure, asthma, and COPD domains and mental health domains | 2020-04-01 | Avanthi Gunasekera | Link to Quality Contract
QOF | National | Network testbed programme launched | 2020-04-01 | Not applicable
Contractual Changes | Contract | All patients will have online access to their full record | 2020-04-01 | Andy Clayton | To note and action as appropriate
Contractual Changes | Contract | Boys added to the HPV catch-up scheme in GP | 2020-04-01 | Not applicable
PCNs | National | New national service specification - Structured Medications Review and Optimisation | 2020-04-01 | Stuart Lakin | To note and action as appropriate
PCNs | National | New national service specification - Enhanced Health in Care Homes | 2020-04-01 | Rachel Garrison | Check overlap with RCCG Care Homes LES
PCNs | National | New national service specification - Anticipatory Care requirements | 2020-04-01 | Rachel Garrison | Check overlap with RCCG Case Management LES
PCNs | National | New national service specification - Personalised Care | 2020-04-01 | Rachel Garrison | To note and action as appropriate
PCNs | National | New national service specification - Supporting Early Cancer Diagnosis | 2020-04-01 | Rachel Garrison | To note and action as appropriate
Workforce | National | Additional Roles Reimbursement Scheme extended to include Physician Associates | 2020-04-01 | Rachel Garrison | To note and action as appropriate
Workforce | National | Additional Roles Reimbursement Scheme extended to include First Contact Physios | 2020-04-01 | Rachel Garrison | To note and action as appropriate
QOF | National | NHS England replace exception reporting system with a more precise 'personalised care adjustment' | 2020-04-01 | Avanthi Gunasekera | To note and action as appropriate
PCNs | National | NHS England will develop 7 specifications and seek to agree these with GPC England as part of annual contract changes | 2020-12-31 | Not applicable
PCNs | National | New Enhanced access services transfer to the Network Contract DES | 2021-03-31 | Sara Hartley | To ensure compliance
Digital | Primary Care | All practices will be offering online and video consultations | 2021-03-31 | Joanne Martin | Link to App
PCNs | National | National network service for cardio-vascular disease case finding requirements start | 2021-04-01 | Rachel Garrison | To note and action as appropriate
| National | National Prevention and inequalities requirements start | 2021-04-01 | Rachel Garrison | To note and action as appropriate
QOF | National | Further changes introduced, including new QI modules | 2021-04-01 | Rachel Garrison | To note and action as appropriate
Extended Access | CCGs | Extended Hours Access DES becomes part of the combined access offer. Joining up urgent care services | 2021-04-01 | Sara Hartley | To ensure compliance
PCNs | National | Prevention and inequalities requirements start | 2021-04-01 | Not applicable
PCNs | National | New national service specification - CVD Prevention and Diagnosis | 2021-04-01 | Rachel Garrison | To note and action as appropriate
PCNs | National | New national service specification - Tackling Neighbourhood Inequalities | 2021-04-01 | Rachel Garrison | To note and action as appropriate
Workforce | National | Additional Roles Reimbursement Scheme extended to include Community Paramedics | 2021-04-01 | Rachel Garrison | To note and action as appropriate
Extended Access | National | Implementation plan following 111/UTC/GP review | 2021-04-01 | Sara Hartley | To note and action as appropriate
Workforce | National | Scheme review will have taken place and renewed guidance will be released | 2024-04-01 | Rachel Garrison | To note and action as appropriate
Non-Contractual | Non-contractual changes for 19/20 | Practices are expected to make progress 2019/20 towards changes that will become contractual requirements in April 2020 (Freedom to speak up, Guardian, Over the counter medicine, temporary residents, Debt and mental health conditions - further detail to follow) | 01/04/2019 - 01/04/2020 | Sara Hartley | To ensure compliance